COUNTRY-LEVEL PROGRAM DOCUMENTATION

PROGRAMME DOCUMENT

- GENERAL INFORMATION

| Title of the Program | International Needs Kenya Education access and retention (EAR) |
| --- | --- |
| Location of the Program | Kenya |
| Program Duration | Continuous |
| Start Date | January 2023 |
| Completion Date | December 2027 |
| Preparation Date | October 2022 |
| Program Budget |  |
| Contact Address | Jocelyn Muraya |
| Telephone Number(s) | +254 707112201 |
| Contact Email | jwmuraya@gmail.com |
| Website (if any) |  |
| Contact Person | Jane Kamau |
| Designation | Project Officer |
| Contact Person’s Email | shirokamaa@gmail.com |
| Program Focal Point | Jane Kamau |
| Contact No. of Focal Point | 0722998689 |
| - INTRODUCTION / BACKGROUND The need to change the Kenyan curriculum was pointed out in the vision 2030 blueprint for national development. A major challenge of the curriculum then (8-4-4) is that it is too rigid and has limited opportunities to align basic education with children’s career interests, aptitudes, and abilities. The system seems to serve best those who score high grades in the traditional subjects (English, Math’s, Sciences, and Humanities) at the end of secondary education, and then proceed for higher education and take up white-collar jobs. There are many children whose aptitude, interests, and abilities lie in vocational education, arts, and sports. It is also worth noting that the Kenyan economy has many (self) employment opportunities in these fields. Furthermore, the job market in the 21stcentury is evolving to create more opportunities in small and micro enterprises rather than the traditional models of employment in careers like teaching, medicine, engineering, etc. It also pointed out that the traditional knowledge-based curriculum suppresses the students’ interests in learning, and prevents them from developing talents and pursuing higher education. The new competency-based curriculum (CBC) came into effect in 2016 with an aim to equip learners with the necessary knowledge, skills, attitudes, and values to achieve the nation’s social, economic, and political aspirations. With an average class size of 60 learners the teachers are overwhelmed, and most learners got lost and did not perform well. The CBC curriculum came to fill in the gap to enable learners learn while also carrying out practical’s. Education access is at the heart of social and economic development of a country. INKE works with local government schools and community schools such as RUSH school Kakamega and Ark Quest in Vihiga County in enabling children access education at both primary and secondary schools. For those who perform exceedingly well they proceed to university or tertiary education. In primary schools INKE has a total of 182 In secondary school we have 94 and in university 24 Despite education being declared by the Government of Kenya to be free, parents are required to pay for tuition, development feeding programs, stationeries, uniforms etc. Most learners come from families that can barely afford to pay the required fees because they are either casual workers, in part time engagement and or industrial workers all of whom earn less than one dollar a day. Hence the education support goes a long way to bridge the gap. With the shift from the 8-4-4 curriculum to the competency-based curriculum most parents and teachers have complained that it takes up a lot of their time and that parents are expected to cough more for the items required for the learner to complete their assignments. The teachers find it difficult to engage and with minimal or no training that went along with the shift they are made to rely on skills they learnt while in college. The main reason for continuation with the school assistance program is because the funds received goes a long way in supporting parents who can barely place a meal on the table to feed their families, it assists in bridging the gap between children who can afford and those who can’t afford. - STATEMENT OF NEEDS Kenya has had a major shift in its education curriculum which has made it more expensive for parents to afford basic requirements such as manilla paper, plasticine, foil etc. Parents have complained that it also takes up a lot of their time and they are required to coach their children in carrying out the homework plus they were ill prepared for this change and the costs it came with. In addition, post covid parents and organizations have been required to cough more to the school fees and other requirements because the school terms are short and there has been a total of four terms per year. Making it difficult for parents to save and or barely scratch the surface in terms of income. This has been detrimental to the economic situation of households and affected the ability of households to contribute more meaningfully to the health and other needs of their families nor meet any other development need of their constituents. - PROGRAMME STRATEGY Strategy: Direct material support to ameliorate suffering of program beneficiaries Direct material support to ameliorate suffering of program beneficiaries Awareness and training to build capacities of the various program beneficiaries Goal To empower vulnerable children and youth through education and training to ensure they realize their full potentials in life To ensure children are protected from exposure to abuse and neglect - PROGRAMME JUSTIFICATION Education is central to development and to the improvement of the lives of young children, youth, families and the community at large. Globally, education has been identified as a priority area in internationally agreed development goals, the Millennium Development Goals and the World Programme of Action for Youth. Education has been identified as key in eradicating poverty and hunger and in promoting sustained, inclusive and equitable economic growth and sustainable development. Increased efforts towards education accessibility, quality and affordability are central to global development efforts. Despite significant improvements in increasing primary school enrolment in Kenya, an attempt to achieving the SDG’s, universal primary level education is unlikely to be met. Moreover, such improvements have not necessarily been followed by an equivalent transition to secondary education, vocational training, non- formal education or entry into the labour market, especially for girls and young women. Above is distribution of population by education as at 2019. In the education spectrum, Kenya has made great progress in recent years, showing the overall potential of education in Kenya. One successful initiative began in 2003, when the Kenyan government rolled out the free primary education (FPE) program, waiving all primary school fees for students. As a result, enrolment in schools tripled. This growth in attendance seems to have occurred nationwide as UNICEF reports that before the COVID-19 pandemic in early 2020 when many schools closed, primary school enrolment in Kenya stood at 99%. World Bank statistics show Kenya’s successes in improving education through FPE and other programs, with the most recent data from 2018 showing a literacy rate of almost 82% for people older than 15 years. This is up significantly from 72.16% in 2007 and 78.73% in 2014. Yet, despite these improvements in literacy and primary school enrollment rates, the schools still charge tuition fees , development fee, books, school feeding and any other educational support requirements that are beyond the reach of most parents making many of the children to drop out to supplement the family income. In 2017, the Kenya Climate Innovation Center reported a 27% dropout rate in primary school. Investing in education is a priority for governments and for charitable organisations like International Needs Kenya in ensuring equitable access and quality, resulting in minimal impact on the lives of learners and decreased opportunities for social participation. In investing in education this will promote the situation of young people, fight extreme poverty, and allow for a maximization of the benefits of globalization for children and youth. - PROGRAMME DESIGN Development Objective To empower vulnerable children and youth through education and training to ensure they realize their full potentials in life. Specific Objective - To enhance access and retention to education for vulnerable school going children - To enable learners to think positive and stay focused, be resilient, build good study habits, manage their time and build strong networks. - To enable learners, develop patience to achieve their goals Expected Outcomes Spiritual development or Value formation - Promotion of integral ministry among disadvantaged communities and children Life Skills and Social development - Strengthened life skills and people development Educational development - Improved access and retention in schools Physical and Health development - Promotion of essential health services to school children and their communities Expected outputs - Strengthened relationship between Church and community in working with children - The capacity of educators in teaching the word of God to children is enhanced - Functional life skills instilled among children and youth - Psychosocial support to children provided - Opportunities for people development identified - Enhanced capacity of educators and teachers - Improved learning environment in schools and rehabilitation centres. - Bridging the gap for pupils and learning needs - Integration of health services within education programs. - Communities are sensitized and supported with preventive health knowledge and skills. Expected Activities and description - Children’s school placements - Children assessment - Children follow ups/school visits - Children psychosocial support - Facilitate vocational training such as metal welding and wood work, college education or university - Give children an opportunity to express their opinions. - Encourage children to express themselves through various activities. - Allow the children to engage in meaningful activities such as engage in meaningful activities such environment clean up exercise Target groups/clientele Children ages 3 to 18 years Women & men Staff Meaningful sponsor relations - Improved sponsor relations for a better quality of life to the children and youth Sustainable funding and administration - Improved capacity of implementing partners to deliver on the education programs |  |
| - PROJECT CROSS-CUTTING ISSUES Gender Analysis-INKE reaches out to children male & female, however our niche is young girls as they are more vulnerable in the community and their needs can be better met as we work with them in the community. INKE is intentional in giving opportunity for employment to female and also reaches out to women in the communities while working with the children. Child Protection- INKE has a child protection and safeguarding policy which it adheres to as it works. There is a form that each employee fills out while working with children and a police check is carried out annually (Certificate of good conduct) Disability inclusion-INKE has not yet developed a policy on disability inclusion, however it is intentional in streamlining children abled differently into every aspects of education and activities that we carry out. In fact in one of our projects we are working with children with cerebral palsy and are intentional in including them in all activities at the Centre. - RISK MANAGEMENT PLAN Risk; Likelihood; Impact; Rating; Mitigation. Direct criminality-Direct criminal activity towards staff, assets belonging to IP’s and beneficiaries; Likely; High; Very high; Robust Safety plan, active monitoring and insurance of property.. Economic deterioration; Likely; High; High; Monitoring of economic situation; contingency planning for programmes. Funding reduction – Significant reduction in funding available to support vulnerable people; Likely; Medium; Medium; Advocacy at Country, Regional and Global levels on the need for funding; planning for priority activities.. Increased regulation – Increasing political regulation, new laws, taxes and requirements at county and local government levels cause financial challenges to operate effective programmes; Possible; Medium; Medium; Engagement and relationship building with national and local authorities. Engagement with NGO forums.. Terrorism-Direct terrorism on partner programmes or staff; Possible; High; Medium; Active monitoring of the situation on the ground. Sound insurance policy effected.. Collapse of the INAP site; Very likely; Very High; Very High; A fire safety risk assessment is in place and cordinate appropriate fire safety procedures to ensure safety of occupants and buildings.. Child abuse by the police; Very likely; Very high; catastrophic; Continue to advocate for the rights of children. Work with other organisations who work with the police force in the child protection area.. - MONITORING AND EVALUATION PLAN MONITORING AND EVALUATION PLAN. Development Goal:. ACTIVITIES; INDICATOR (s); BASELINE; TARGET; FREQUENCY (How often will it be measured?); MEANS OF VERIFICATION; RESPONSIBLE; REPORTING. What is the current value?; What is the target value?; Year 1; Year 2; Year 3; Year 4; Year 5; Who will measure it?; Where will it be reported?. 1.0 Organize summer reading clinic for 200 students; Number of students who completed summer reading clinic; 0; 200; 20; 20; 45; 55; 60; Summer camp attendance records, Activity Pictures; Program Officers; Quarterly Project Reports. Payment of school fees for Highschool and primary school children; % of children enrolled in school %of children accessing and being retained in school; 0; Records of the number of new children entering school School register Receipts; Project officer; Quarterly report. Paying college fee for college children; Number of children paid for in secondary school; 0; Records of the number of new children entering school School register Receipts; Project officer; Quarterly report. Purchasing school uniforms for the form one high school children.; Receipts Pictures; Project officer; Quarterly report. Purchasing stationery for Children Joining Form one; Receipts pictures. Enrolling children into 30 teenagers in bible class; Receipts showing payments made Enrollment in school register and attendance register. Sensitizing 50 caregivers on children rights and academic area so as to enlighten the community; % of caregivers articulating child rights in the community % of caregivers able to take action when theres a violation % of caregivers able to pass on the messages of child rights. - PROJECT ACTIVITY SCHEDULE Activities. Payment of school fees for Highschool and primary school children. Paying college fee for college children. Purchasing school uniforms for the form one high school children.. Purchasing stationery for Children Joining Form one. Enrolling children into 30 teenagers in bible class. Enrolling and educating 30 young mothers into health education. Purchasing food basket for the 5 neediest cases. Purchasing food basket for the 50 neediest cases. Motivating the best child in all areas, curriculum and extra curriculum area. Enrolling children in Rite of passage classes. Remedial classes for poorly perfoming children. Capacity building. Sensitizing 50 caregivers on children rights and academic area so as to enlighten the community. Trainging 45 girls on cleanlingless during their mestrual period. Purchasing School uniforms for the most needy cases for primary sch children. Motivating the best child in all areas, curriculum and extra curriculum area. Boys to Men Program that mentors boys to be responsible men.. Fathers Engagement Serminar. Team building for caregivers and benefeciary. Puchasing Office dedicated phone. - PROGRAMME BUDGET INKE INAP Five year budget. Item; Detail; Year one; Two; Three; Four; Five. Target. School fee payment for both primary and secondary schools; 550; 10,800,219; 11,340,230; 11,907,242; 12,502,605; 13,127,736. Monitoring school visits; 100,000; 102,000; 104,040; 106,121; 108,244. Payment of university & college fees for students; 700,000; 735,000; 771,750; 810,338; 850,855. Purchase of books, uniforms & required items for form one placement; 300,000; 350,000; 400,000; 450,000; 500,000. Sensitizing 190 parents and guardians on child rights and academic clinics; 300,000; 313,000; 320,000; 322,000; 332000. Training 45 annually girls on health & hygiene during menstrual season; 200,000; 220,000; 240,000; 260,000; 280,000. Fathers’ engagement seminar; 150,000; 180,000; 200,000; 230,000; 250,000. Remedial classes for below average performers; 500,000; 432,000; 480,000; 500,000; 500,000. Boys to men & girls to women education. Total; 13,050,219; 13,672,230; 14,423,032; 15,181,064; 15,948,835. USD; 113,480.17; 118,888.96; 125,417.67; 132,009.25; 138,685.52. Grand total Ksh; 72,275,380. Grand Total in USD; 628,481.57. |