COUNTRY-LEVEL PROGRAM DOCUMENTATION

INLK’s INAP PROGRAMME DOCUMENT

- GENERAL INFORMATION

| Title of the Program | SL Emerge |
| --- | --- |
| Location of the Program | Mullaitivu District, Vavuniya, Monaragala, Matara |
| Program Duration | 3 years |
| Start Date | January 1, 2023 |
| Completion Date | December 31, 2025 |
| Preparation Date | November 27, 2022 |
| Program Budget | USD 136,585.00 |
| Contact Address | 301/1, ½, Kotte Road, Nugegoda, Sri Lanka |
| Telephone Number(s) | +94777155392 |
| Contact Email | inlk@internationalneeds.global |
| Website (if any) |  |
| Contact Person | NarenDharmanandan |
| Designation | Chief Executive Officer – INLK |
| Contact Person’s Email | naren@internationalneeds.global |
| Program Focal Point | Averille Ananth |
| Contact No. of Focal Point | +94777155392 |
| - INTRODUCTION / BACKGROUND The introduction is an initial pitch of the intended program. It sets the scene and tone for the general content of the document. This includes a description of the school / community, history of INAP in the school / community, the problem statement, statistical information, actions undertaken by various stakeholders in the past and present, organizational involvement and contributions. Indicate the current situation in the field of education in the community you want to work in. How many schools are there? How are school attendance rates? How is the education overall in the country you work in? Are there any specific reasons why you want to start or continue the assistance programme in the school or community? Sri Lanka is an island country in South Asia, with a total population of 21.92 million (Census 2020), with diverse ethnicities and languages. There is an annual population growth rate of 1.14%, with a birth rate of 17.6 per 1,000 people and the date rate of 6.2 per 1,000 people. The population density is highest in western Sri Lanka, and the largest ethnic group is Sinhalese community with Sri Lankan Tamils constituting the second major ethnic group. There are smaller ethnic groups such as the Burghers (of mixed European descent), Malays from Southeast Asia, as well as a small indigenous population called the Vedda people. For administrative purposes, Sri Lanka is divided into 9 provinces and 25 districts. Each district is further subdivided into divisional secretariats (totalling 256) and these into Grama Niladhari divisions (14,008). Sri Lanka currently finds itself in a particularly defining moment in its history; grappling with a nosediving economy, food and fuel shortages, as its’ largest industries of tourism and garment production and exports have taken a hit post-terror attacks in 2019, and post-COVID. Outside of the main urban cities, these shortages are further exacerbated due to transportation issues. Food supply has significantly taken a dip as the government instituted a chemical fertiliser ban, leaving the agriculture industry and small farmer struggling to afford organic fertilisers. This has led to a large public outcry across the island, demanding that the current political regime (as it is a majority parliament) resign and allow younger and more meritocratic leadership to take its place. International Needs Lanka (INLK) began serving communities in Sri Lanka in 1998, within under privileged communities in the capital city in the area of education and children’s rights. Since then INLK has grown to serve communities in various regions across the island nation – in the North, Central and Western Provinces – expanding to women’s empowerment and livelihood programming. INLK’s mission is ‘Empowering the marginalized to restore human dignity – their physical, emotional, social and spiritual identity.’ Working in the regions with varying needs, with individuals of varying beliefs and backgrounds, INLK aims to see holistic change occur within these communities spearheaded by their own community members. INLK’s vision is ‘Transformed lives. Transformed communities.’ INLK is re-introducing INAP to the programming; as it has been largely inactive over several years. INLK has been working with INA with a group of ChildLink kids families sponsored over the last 5 years. This project design is focused on interventions that enable children and youth receive a robust and holistic foundation – education up till graduation, and post-secondary should they choose, as well as pathways to employment, a healthy environment and access to medical system, and the opportunity to discover their faith. Northern district, which In the North, the after effects of the war which concluded in 2009 continue to be seen. It is estimated that the war killed 100,000 people and close to a million were displaced. Mullaitivu district sheltered thousands of Sri Lankans within displacement camps. Mullaitivu is situated on the North Eastern coast of Sri Lanka. Even though the war ended over a decade ago, the struggle for safe and dignified lives continue. Within the Mullaitivu district is the division Puthukkuddiyiruppu (PTK) whose total population is just over 41,000 persons, of which 12% of women are widowed due to the war, accidents and missing spouses; a disabled population of 1063 adults and children. 99% of the population are Tamil and 87% are Hindu. The area is part of the arid northwest or “dry zone” and receives the least rain of about 800- 1,200mm per year. Background of Nochikulam and Monaragala - STATEMENT OF NEEDS Generally, this will include identification of the problem, A description of the needs identified and an analysis of development needs. It gives a sense of the scope of the problem and helps the reader of the programme document to establish the relevance and importance of your proposed programme. It is also a prime opportunity to link the relevance of your proposed intervention/solutions to the strategic interest and goals of the sponsor. Poverty is the issue that has the largest impact on the communities and families within it. Irregular and low incomes, lack and discrimination in opportunities and wages for women, poor access to jobs for different age groups and the disabled are some of the causes of poverty. These directly affect the children and youth, as it limits the opportunities to pursue education for children – due to needs for funds for uniforms, travel and school supplies; and youth are limited to post-secondary and employment. The name “Puthukkuddiyirrippu” in Tamil translates to new resettlement – as the land in this area was granted to displaced populations from Mannar, Vavuniya, Kilinochchi and Jaffna Districts after the conclusion of the war in 2009. These war-affected communities were resettled without sound resettlement plans, therefore the recovery programmes run by the government have not had an effective impact. The majority of the population was resettled by the government into these regions and granted land of about quarter to a half acre of land; which is within the dry zone as mentioned earlier. The land alone is barely sufficient for sustenance; as the small household gardens are not productive enough, due to high salination levels. The resettlement plans also included LKR 500,000 per family for housing construction, however the total cost exceeded nearly double for each household, forcing families to obtain loans to complete construction. During the initial resettlement process, although there were some attempts by non-governmental organisations to initiate livelihood support, these were not sustainable due to a lack of follow-up support and monitoring, and lack of training provided. The allocations for housing have also created the issue of isolation, as households have been resettled without being fully integrated within the community as well as caste differences, and hesitance to accept ex-LTTE combatants and ex-employees is also apparent. There is one school about three kilometres away from these villages within PTK, with classes up to Grade 12, and the closest school which is two kilometres away has classes up to Grade 9. Transportation is an issue as public bus service is poor and difficult for children to commute in these buses; and not all children own bicycles. Most children study up to Grade 9, but are unable to commute in order to complete the standard examinations of GCE O/L and A/L. There is one vocational trainer within the area, however the larger issue is that trained youth are not able to obtain jobs – the youth in the area lack access to information on relevant education and jobs available. In addition, a large percentage of youth are not able to meet the minimum education prerequisites for enrolling in vocational programs. (waiting on needs assessments reports for the following areas) Nochikulam in Vavuniya - Limited access to education, only school up to Grade 5 - Little to no access to water - Some agriculture in the area - Domestic abuse/ family issues Kadurugodagama in Monaragala - An area which sees the least rainfall throughout the year, therefore nutrition is less. - Children don’t have access to school, due to dangerous terrain and no teachers in their area - Abuse and neglect of children - PROGRAMME STRATEGY A strategy is more about a designed set of options other than a fixed plan of what will be achieved. This generally communicates broad concepts or approaches to achieve the objectives of the programme. It outlines the detailed plan of actions designed to achieve a major or overall goal. This Project aims at addressing the issues of educational gaps for children and youth, improved health, better financial stewardship to ensure a robust foundation in helping eradicate poverty. Food security and income instability hampers the ability of families to envision and pursue dreams for themselves and their children. This creates a disillusionment of youth, which requires intervention. To address education gaps, and employment opportunities for children and youth: - Sensitizing children and youth who are at risk into learning programs, run by community leaders within PTK. - Provide English literacy education for children and for youth - Partner with government to better equip teachers with updated training methods, and to provide additional teaching for students that require - Sponsor youth to access post-secondary education online - Create pathways to accessing internships and employment in cities/ towns close to their villages - Train youth with job readiness skills – looking for employment, application for jobs, and interviewing skills The project aims to improve the health faced by the communities and improve standard of living by addressing through: - Construction of water tank in village of Kadurugodagama in Monaragala, and provide water lines for each family. (Possibly for the other village as well) - Conduct WASH awareness and training. - Carry out mobile health clinics annually - Continue providing nutritious meals for children at classes The project aims to improve the economic instability and improve standard of living by addressing income through: - Supporting livelihoods programs for households within the communities in Mullaitivu, Nochikulam and Monaragala. The beneficiaries will be identified by mobilisers and the local government. Livelihoods programs that will focus on agriculture and cultivation (peanuts), animal husbandry (poultry and goat rearing) and other entrepreneurial activities. These livelihoods beneficiaries will include community leaders who have also been badly affected by the issues in the area – post-COVID and economic crises in the country. - Financial stewardship training across all the communities - Trainings on agriculture, animal husbandry and running a business for households engaged in the livelihoods program across all communities - PROGRAMME JUSTIFICATION This basically explains why your project is necessary and what it will do?Which benefit will the project have?Which positive effects will it have?Which new chances could open up for the intended beneficiaries because of the project?Which problems will be solved by your project?How do these problems affect your community or school at the moment? To ensure longer term success and sustainability; this program aims to launch a training program methodology with the goal of sensitizing some of the most important stakeholders – children and youth towards the importance of learning and the opportunities it could lead to. The sensitization programs run by community leaders within the villages brings a sense of responsibility and the dissemination of information then continues past the project life cycle.Conducting these sensitization programs can also encourage and inspire the other beneficiaries involved (the older generation) as they continue building their livelihoods and small businesses. These address the financial stability issues, in addition to the workshops related to financial stewardship and livelihoods, which will create a more secure foundation for the children. - PROGRAMME DESIGN - Development Objective - Specific Objectives - Expected Outcomes (educational, life skills and social development, physical and health, spiritual and value formation) - Expected Outputs - Expected Activities and Description - Target Groups / Clientele - Meaningful Sponsor Relations - Sustainable Funding and Administration |  |
| - PROJECT CROSS-CUTTING ISSUES - Gender Analysis - Child Protection - Disability Inclusion - RISK MANAGEMENT PLAN The plan tells how to deal with specific risks and what management actions must be taken against those risks to mitigate or remove threats to the programme tasks and outcomes.The risk management plan gives all stakeholders a sense of measures they need to take to identify, analyze, and respond to all the risks running around within the project wheel. - MONITORING AND EVALUATION PLAN The M&E plan helps to track and assess the results of the interventions throughout the life of the programme. It is a living document that should be referred to and updated on a regular basis. A recommended outline of an M&E plan should include programme goals and objectives, theory of change, indicators, table with data sources, collection timing, and staff member responsible, roles and responsibilities, description of each staff member’s role in M&E data collection, analysis, and/or reporting, description of how and when M&E data will be disseminated internally and externally. - PROJECT ACTIVITY SCHEDULE An activity schedule is an analytical tool for graphically presenting and reviewing the activities of a project. It helps to identify the logical sequence of the activities, estimate their duration, and denote any dependencies that exist between them. The activity schedule also serves as a foundation for allocating management authority and responsibility. Typically, the columns must capture a list of all activities with timelines and persons responsible. - PROGRAMME BUDGET Description; Year 1; Year 2; Year 3; Total Cost (USD). Outcome 1.1 Increased school attendance and access to e-learning for children. 1.1.1 Train community leaders in conducting sensitization training for the importance of education; 200.00; 100.00; 100.00; 400.00. 1.1.2 Form of children’s groups to conduct sensitization training re. importance of education and leadership building programs; 350.00; 350.00; 350.00; 1,050.00. 1.1.3 Conduct English literacy trainings for children in Grades 1-5; 2,040.00; 2,040.00; 2,040.00; 6,120.00. 1.1.4 Partner with the local schools and teachers to provide teacher training on methodology and preparation of teaching aids; 100.00; 100.00; 100.00; 300.00. 1.1.5 Provide children's uniforms and school supplies yearly; 1,650.00; 1,650.00; 1,650.00; 4,950.00. 1.1.6 Monitor the project INCAP and INGAP programming.; 100.00; 100.00; 100.00; 300.00. Output 1.2 Improved access to post-secondary education and employment for youth. 1.2.1 Train community leaders in conducting sensitization trainings re. importance of post-secondary education and job preparedness; 100.00; 100.00; 100.00; 300.00. 1.2.2 Conduct sensitization training for youth re. importance of post-secondary education, and job preparedness – ie job searching, interview skills etc; 345.00; 345.00; 345.00; 1,035.00. 1.2.3 Conduct English and Sinhala literacy trainings for youth seeking post-secondary education and employment opportunities in larger cities; 330.00; 330.00; 330.00; 990.00. 1.2.4 Identify and support (sponsor) youth for vocational training programs at post-secondary level; 5,000.00; 5,000.00; 5,000.00; 15,000.00. 1.2.5 Establish relationships with partners in commercial hubs – in cities close to PTK and in Colombo for suitable employment streams for youth; 200.00; 200.00; 200.00; 600.00. 1.2.6 Monitor the INSAP programming.; 200.00; 100.00; 100.00; 400.00. Outcome 2.1 Improved health condition of children. 2.1.1. Build water tank and water distribution system for community; 18,500.00; 200.00; 200.00; 18,900.00. 2.1.2 Conduct awareness and training for use for community members on the use of new water lines and WASH.; 100.00; 100.00; 100.00; 300.00. 2.1.3 Monitor WASH related project activities.; 100.00; 100.00; 100.00; 300.00. Outcome 2.2 Improved access to potable/ safe drinking water/ Reduced cases of waterborne diseases. 2.2.1 Conduct mobile health clinics (health check-ups) annually; 500.00; 500.00; 500.00; 1,500.00. 2.2.2 Provide nutritious meal for children at classes weekly.; 1,500.00; 1,500.00; 1,500.00; 4,500.00. 2.2.3 Monitor Health related project activities.; 100.00; 100.00; 100.00; 300.00. Outcome 3 Increased knowledge re. income-generating opportunities, enabling families to meet basic needs of all members. 3.1.1 Conduct training for Self Help Groups on initiating and managing livelihoods projects; 300.00; 300.00; 300.00; 900.00. 3.1.2 Conduct financial stewardship for community members, and youth.; 300.00; 300.00; 300.00; 900.00. 3.1.3 Monitor livelihoods and financial stewardship activities.; 150.00; 150.00; 150.00; 450.00. Outcome 4 Increase in awareness about faith and equipped with. 4.1.1 Outreach program conducted for communities for Christmas and Easter; 3,000.00; 3,000.00; 3,000.00; 9,000.00. 4.1.2 Conduct "Joyful Family" counselling for families.; 100.00; 100.00; 100.00; 300.00. 4.1.3 Monitor the faith outreach and counselling activities.; 100.00; 100.00; 100.00; 300.00. Project baseline and evaluation. 5.1.1 Project baseline study; 300.00; 300.00. 5.1.2 Project evaluation; -; 500.00; 500.00. Direct Project Support Cost 6. 6.1.1 Direct Project Staff Cost; 3,000.00; 4,650.00; 6,000.00; 13,650.00. 6.1.2 Field travel, subsistance, vehicle running maintenance and Administration; 840.00; 840.00; 840.00; 2,520.00. 6.1.3 District Operational cost; 200.00; 200.00; 200.00; 600.00. 6.1.4 Project Monitoring & Administration; 1,400.00; 1,400.00; 1,400.00; 4,200.00. Total - Direct Project Cost; 41,105.00; 23,955.00; 25,805.00; 90,865.00. Support Costs 7. 7.1.1 INLK Administration Charges; 7,500.00; 7,500.00; 7,500.00; 22,500.00. 7.1.2 Project Coordinator's Salary; 5,160.00; 5,160.00; 5,160.00; 15,480.00. 7.1.3 Monitoring & Evaluation Officer's Salary; 2,580.00; 2,580.00; 2,580.00; 7,740.00. Subtotal Support Costs; 15,240.00; 15,240.00; 15,240.00; 45,720.00. TOTAL; 56,345.00; 39,195.00; 41,045.00; 136,585.00. |