COUNTRY-LEVEL PROGRAM DOCUMENTATION - NEPAL

PROGRAMME DOCUMENT

1.  	GENERAL INFORMATION

| Title of the Program | Nepal Assistance Program (NAP) |
| --- | --- |
| Location of the Program | Nepal |
| Program Duration | Five years |
| Start Date | April 2023 |
| Completion Date | March 2027 |
| Preparation Date | Nov 2022 |
| Program Budget | USD 921,000 |
| Contact Address | Lalitpur, Nepal |
| Telephone Number(s) | +977 5590224 |
| Contact Email | malati_p@innepal.org |
| Website (if any) | www.innepal.org |
| Contact Person | Uma Magar |
| Designation | Deputy Executive director |
| Contact Person’s Email | uma_magar@innepal.org |
| Program Focal Point | Malati Pandey |
| Contact No. of Focal Point | +977 9801236557 |
| 2. INTRODUCTION / BACKGROUND International Needs Network Nepal (INNP) is one of the partners of Global IN ministry. Inspired and mandated by God’s commandment, IN Nepal is serving the needy individuals and communities for more than three decades with the support of IN support countries. INNP strives to contribute for transformed lives, changed communities, working in four programs namely; Children Education Program, Community Development Program (CDP) focusing on equipping church leaders for Integral mission, Women Empowerment Program (WEP) focused on skill development of women for inco me generation through Lydia vocational training program and the Livelihood program (LHP) to support the livelihood of poor and vulnerable rural communities. Since more than three decades IN Nepal is serving the needyfamilies/communities/individuals with an aim to bring positive change in their lives through mobilizing the local church leaders known as a Community Workers (CW). These CW represent the community, live in/with the communities in different parts of the country. Landlocked, inadequate infrastructure, deeply rooted in patriarchal background, Nepal is one of the least developed nations in the world..More than half of Nepal’s population is composed of Women (54.19%) and children. The 2011 census shows a huge disparity in the literacy rate male ( 71.1%) and female (46.7%). Poverty, social discrimination, poor access to education and facilities, orphanage and poor family status, malnutrition, high child labor, child marriage are some of the issues facing Nepal. A vast majority of the population is Hindu with a small percentage following Buddhism and other religious faiths. Christians officially makes of 1.4% of population while the unofficial data claims it to be 4%. Proselytizing is strictly prohibited and considered to be a punishable crime. Poverty, poor education facility, gender discrimination are some of the obstacles to development in Nepal. IN Nepal has prioritized these key areas to intervene to bring about a positive change in the lives of individuals and communities. The introduction is an initial pitch of the intended program. It sets the scene and tone for the general content of the document. This includes a description of the school / community, history of INAP in the school / community, the problem statement, statistical information, actions undertaken by various stakeholders in the past and present, organizational involvement and contributions. Indicate the current situation in the field of education in the community you want to work in. How many schools are there? How are school attendance rates? How is the education overall in the country you work in? Are there any specific reasons why you want to start or continue the assistance programme in the school or community? 3. STATEMENT OF NEEDS Poverty in Nepal is a gendered issue and the incidence of poverty falls disproportionately on women and girls. Nepal carries a legacy of a hierarchical social structure based on gender, caste and ethnicity, poverty has a strong social dimension. Food self-sufficiency is much lower among socially excluded people, single women where poverty is the highest. Similarly, they are far behind in education and health outcomes. Despite comprising half of the country’s population, women fall victim of discrimination and various gender based violence. In terms of earning, women are involved in domestic chores and unpaid work. In the urban areas, women and girls are engaged in informal, low-paid, menial formal work, for example in the garment industry, domestic work such as cleaning, cooking, and caring for children, sick and elderly. Their labour and contribution does not translate into improved socio-economic status for them. National Planning Comission (NPC) has reported on Overview of Millennium Development Goals (MGD) outcomes that Gender inequality in employment and incomes persisted, mostly due to women‘s lower skill levels and their unpaid care responsibilities. Gender differences in wages for the same level of work also persisted over years (Nepal’s Sustainable Development Goals Baseline Report 2017, NPC). Despite some significant and continuous improvement in policies reformation and women rights, discrimination and violence against women and girls’ is a still a common practice The status of women remains very poor in terms of health, education, income, decision-making. COVID -19 Pandemic hit Nepal very hard and it inevitably had a negative impact on women and girls making them more vulnerable, resulting in an increase in incidence of domestic violence. Nepal is still working to provide quality education to its population from an early age. Various Campaign schemes, with the support of national and international agencies to educate parents, children, and families, improve schools, develop curriculums, and develop teachers' capacity were conducted. Although families are aware of education and its need, various factors such as poverty, and lack of convenient school locations are preventing children from access to education. Not all the children who got enrolled may not complete their education and become qualified citizens/ Workforce. As per the Government of Nepal National Planning Commission Central Bureau of Statistics and UNICEF’s Multiple Indicator Cluster Surveys 2019, In Nepal, 82% of children complete lower basic schooling, and 75% complete upper basic school. However, only 27% of children in Nepal complete secondary school while 15% of secondary school-age children are out-of-school. These data indicate a great need to prevent children from dropping out of school as they transition into secondary school. [1] Generally, this will include identification of the problem, A description of the needs identified and an analysis of development needs. It gives a sense of the scope of the problem and helps the reader of the programme document to establish the relevance and importance of your proposed programme. It is also a prime opportunity to link the relevance of your proposed intervention/solutions to the strategic interest and goals of the sponsor. 4. PROGRAMME STRATEGY Major Strategies: - Financial Assistance - Provide financial assistance to child, student, womens and workers - Empowerment - enhancing the capacity of women through skill training/vocational training. - Protection - Raising awareness and educating children, women and students on their rights, legal provisions and risks and vulnerability to exploitation. - Equipping Community Workers from diverse ethnic groups/ communities for social mobilization. - Economic Empowerment - Entrepreneurship development through business training and start up support such as seed money/ microloan. - Linkage and referral - to protect child/ women at risk of exploitation, abuse and further legal or psychological counseling (protection) - Networking and collaboration - coordination and collaboration with government authorities, Churches and like - minded organizations for awareness raising and advocacy initiative. - Peer Learning - through alumni platform and experience sharing with like-minded organizations. A strategy is more about a designed set of options other than a fixed plan of what will be achieved. This generally communicates broad concepts or approaches to achieve the objectives of the program. It outlines the detailed plan of actions designed to achieve a major or overall goal. 5. PROGRAMME JUSTIFICATION Education: Although education has been identified as a necessity, families are still struggling to make it available to their children due to low economic background and various family problems. As the living cost is increasing exponentially than the rate of income many children and students had to drop out from the school. The education program intends to provide assistance to those families and students who couldn't afford to send their child to the school or afford the higher education. This will enable the families and students to have continued education and develop educated citizens to have a better life and contribute back to society. Women Empowerment : SDG 5 aims to achieve gender equality and empower all women and girls by the end of 2030. In Nepal,women have been denied their fundamental rights such as right to health, education and safety, let alone reaching their full potential or chasing their dream. A vast majority of women in Nepal born in poverty, live their entire life struggling and fighting multiple vulnerabilities and challenges. Due to patriarchal background, socio-cultural structure, systemic discrimination, self-stigmatization, and lack of education and awareness, women are open to multiple vulnerabilities such as child marriage, sexual and domestic violence, trafficking, unsafe migration and wage theft. The project is intended to empower and enhance the capacity of poor and vulnerable women across Nepal so that they are develop confidence for their own welfare and they no more have to bear the continued weight of discrimination and violence against them. The project seeks to improve the quality of life of women living in the underprivileged, rural or urban communities by providing them with skills and tools to improve their economic condition. In addition, educate and make them aware about the potential risks to protect them from exploitation. This will improve their socio-economic situation and bring them in a stronger position and capacity to make their livelihood and make decisions that promote their own health and wellbeing, as well as that of their families. Community Workers Support : Christianity falls under minority groups in the context of nepal. Having a strong influence of hindu backed leaders and society many lives are still unaware about the love of Christ. Proselytizing is illegal in Nepal, yet many churches are trying their best to reach the unreachable people and communities. INNP, through NAP will providing an assistance to This basically explains why your project is necessary and what it will do. Which benefit will the project have? Which positive effects will it have? Which new chances could open up for the intended beneficiaries because of the project? Which problems will be solved by your project? How do these problems affect your community or school at the moment? 6. PROGRAMME DESIGN a. Development Objective- To uplift the socio-economic conditions of poor and underprivileged communities of Nepal through equipping and empowering women and community leaders and ensuring education for children and students. b. Specific Objectives: - To provide financial assistance for 700 students and 55 community workers to ensure the continuation of their education and social mobilization. - To enhance skills and capacity of 300 poor and vulnerable women /girls so that they are able to secure their livelihood and self esteem. - To provide Income Generating Activities support (Seed money/microloan) for start up and upgrading of 25 women initiated businesses. - To raise awareness about risks of Gender based violence and legal provisions to protect women from abuse and exploitation. - To provide awareness and career counseling to the children for higher education c. Expected Outcomes (educational, life skills and social development, physical and health, spiritual and value formation) - Supported children have completed their schooling. - Beneficiary students acquire jobs after completion of education and their family’s economic condition is improved. - Life skills- women and school children making career and life decisions for themselves and their future. - Improved socio-economic conditions of poor and vulnerable women through micro businesses. - Reduction in incidence of gender based violence in the communities/families - Churches strengthened and community people accepted Christ. d. Expected Outputs - 600 Supported children’s access to education ensured - Enhanced capacity and opportunities for 300 women and girls through skill training and micro-loan support by the end of 5th year. - 50 Women initiated micro businesses in operation. - 52 Community workers equipped for social mobilization. e. Expected Activities and Description - Provide support for the 600 children/ 70 students/ 55 workers - Conduct awareness classes for 200 children and students annually - Run extra classes/ tuition classes for 30 INGAP students annually - Distribute funds for uniforms, books,s, and stationaries to INGAP beneficiaries - Organize medical checkups for 30 INGAP Students - Organize gift distribution programs - Organize an annual gathering of the children and students - Conduct Alumni meetings and experience-sharing - Conduct five months of Lydia tailoring training - Organize career counseling sessions for Students - Conduct Capacity building training for Community Workers - Distribute equipment for the community works for travel and local coordination - Develop Curriculum for Community leadership training - Conduct education and Awareness classes for women - 2000 women - Conduct Life skills training for women and girls 150- 200 - Digi classes (computer literacy) for Lydia and local community women-100 - Organize women’s network meetings and advocacy program for women - Organize Business training for women entrepreneurs -150 - Distribute Seed money/microloans for businesses started by women-25 businesses - Conduct monitoring and follow-up visits - Conduct program midterm and final evaluation (external) - Conduct network meetings and peer learning sessions through Alumni - Develop curriculum for Lydia's training - Distribute sewing machine for Lydia's ladies - Distribute hygiene kits for Lydia ladies and community women f. Target Groups / Clientele · Poor and vulnerable students/ families from rural, marginalized and urban poor communities · Poor and vulnerable women from rural and urban poor communities · Community worker/ leaders/ pastor/ evangelist g. Meaningful Sponsor Relations Following measures will be taken to develop and maintain a meaningful donor-relation - Timely communication with support partners concerning all the program (planning, implementation, updates on revisions, challenges and learnings) - Compliance to reporting schedule, sharing updates- the Link and other reporting mechanism - Inviting support partners and donors for monitoring and field visits - Maintaining consistency in sharing updates on policies, major changes in the governance, project beneficiaries, or any other challenges, risks and lessons learned. h. Sustainable Funding and Administration IN Nepal being a non profit making NGO, rely on donor funding to implement and manage its programs. However, to ensure the continuation of the programs in absence of continued funding, following steps are taken - Establish and operate a social enterprise to manufacture and sell the products to make income for supporting women empowerment and funding micro-businesses. - Establish a revolving fund among the local women group/Lydia alumni so that they can sustain themselves. - Create and maintain a reserve/contingency fund to continue the programs if the funding is stopped. |  |
| 7. PROJECT CROSS-CUTTING ISSUES a. Gender Analysis INNP through NAP ensures gender equity in all program interventions. NAP provides equal opportunities to both men and women. Having a deep-rooted history of patriarchy, NAP intentionally provides added priorities to the girl/ women beneficiaries.INNP also ensures the full compliance to the organizations Gender Equality and Social Inclusion (GESI) policy. b. Child Protection Being one of the organizations working among the children, INNP has strong child protection policies.The policies are well oriented, aware and practiced in organization and among stakeholders. c. Disability Inclusion INNP tends to provide more of its services to the people with disabilities. INNP categorizes disability as multidimensional vulnerable and prioritizes those beneficiaries in every aspect of the program. 8. RISK MANAGEMENT PLAN Risks; Likelihood; Mitigation Plan. Political instability - Change in political power due to an election may also affect the project; High; Mobilizing the local women’s groups and Community workers will ensure good rapport if there is any change in local government. high surveillance - being a Faith Based organization and the government being very strict against evangelism and proselytizing.; High; Being sensitive while reporting and documentation. No visible religious components and no discrimination in beneficiary selection.. Natural Disasters- Nepal is vulnerable to landslide, flood and earthquake; High; Plan monitoring and follow - up in low risk months and avoid intensive travel and key activities during monsoon.. Shifting of the family's resident; Medium; Orientation and proper channel of communication will be maintained. New children will be identified, informed, and replaced. 9. MONITORING AND EVALUATION PLAN In order to examine and measure/track the project progress M&E team consisting of Project lead and M&E officer will make field visits. The data collected will be analyzed/ audited, lessons learned will be used to formulate effective implementation strategy and actions. In addition, the event reports, beneficiary experience sharing, feedback, quarterly and annual reports based upon a set of pre-identified indicators will provide a picture of the project progress. The feedback and learnings will be used to revise and refine the activities and inputs to ensure the quality of outputs and outcomes. Similarly, project review meetings will be organized on a quarterly basis to review the progress and any need for revision to achieve the desired outcome. The support partner will also visit the project location to monitor and assess the progress as and when feasible. Program effectiveness will be evaluated through comparative analysis of the pre and post program enrollment on the basis of their attitudes, practices, behavior, economic condition and relationship. Mid term and final evaluation will be done by the Social Welfare Council and through employing an independent external evaluator. 10. PROJECT ACTIVITY SCHEDULE Activity; Year 1; Year 2; Year 3; Year 4; Year 5. Quarters; 1; 2; 3; 4; 1; 2; 3; 4; 1; 2; 3; 4; 1; 2; 3; 4; 1; 2; 3; 4. Dispatch support for the children/students/workers. Conduct awareness classes for children and students. Run extra classes/ tuition classes for INGAP students. Distribute funds for uniforms, books,s, and stationaries. Organize medical checkups for INGAP Students. Organize gift distribution programs. Organize an annual gathering of the children and students. Conduct Alumni meetings and experience-sharing. Conduct five months of Lydia tailoring training. Organize career counseling sessions for Students. Conduct Capacity building training for Community Workers. Distribute equipment for the community works for travel and local coordination. Develop Curriculum for Community leadership training. Conduct education and Awareness classes for women. Conduct Life skills training for women and girls. Digi classes (computer literacy) for Lydia and local community women. Organize women’s network and advocacy program for women. Organize Business training for women entrepreneurs. Distribute Seed money/microloans for businesses started by women. Conduct monitoring and follow-up visits. Conduct program midterm and final evaluation (external). Conduct network meetings and peer learning sessions through Alumni. Develop curriculum for Lydia's training. Distribute sewing machine for Lydia's ladies. Distribute hygiene kits for Lydia ladies and community women. 11. PROGRAMME BUDGET |

| Activities | Y1 | Y2 | Y3 | Y4 | Y5 | TOTAL USD |
| --- | --- | --- | --- | --- | --- | --- |
| Dispatch support for the children/students/workers | 59,600 | 65,560 | 72,120 | 79,330 | 87,260 | 363,870 |
| Conduct awareness classes for children and students | 430 | 470 | 510 | 570 | 620 | 2,600 |
| Run extra classes/ tuition classes for INGAP students | 3,900 | 4,290 | 4,720 | 5,190 | 5,710 | 23,810 |
| Distribute funds for uniforms, books,s, and stationaries | 1,200 | 1,320 | 1,450 | 1,600 | 1,760 | 7,330 |
| Organize medical checkups for INGAP Students | 600 | 660 | 730 | 800 | 880 | 3,670 |
| Organize gift distribution programs | 3,990 | 4,390 | 4,830 | 5,310 | 5,840 | 24,360 |
| Organize an annual gathering of the children and students | 830 | 920 | 1,010 | 1,110 | 1,220 | 5,090 |
| Conduct Alumni meetings and experience-sharing | 830 | 920 | 1,010 | 1,110 | 1,220 | 5,090 |
| Conduct five months of Lydia tailoring training | 29,610 | 32,570 | 35,820 | 39,400 | 43,340 | 180,740 |
| Organize career counseling sessions for Students | 330 | 360 | 390 | 430 | 480 | 1,990 |
| Conduct Capacity building training for Community Workers | 8,500 | 9,350 | 10,290 | 11,310 | 12,440 | 51,890 |
| Distribute equipment for the community works for travel and local coordination | 6,000 | 6,600 | 7,260 | 7,990 | 8,780 | 36,630 |
| Develop Curriculum for Community leadership training | 3,600 | 3,960 | 4,360 | 4,790 | 5,270 | 21,980 |
| Conduct education and Awareness classes for women | 830 | 920 | 1,010 | 1,110 | 1,220 | 5,090 |
| Conduct Life skills training for women and girls | 830 | 920 | 1,010 | 1,110 | 1,220 | 5,090 |
| Digi classes (computer literacy) for Lydia and local community women | 1,670 | 1,830 | 2,020 | 2,220 | 2,440 | 10,180 |
| Organize women’s network and advocacy program for women | 710 | 780 | 860 | 940 | 1,030 | 4,320 |
| Organize Business training for women entrepreneurs | 4,810 | 5,300 | 5,830 | 6,410 | 7,050 | 29,400 |
| Distribute Seed money/microloans for businesses started by women | 4,170 | 4,580 | 5,040 | 5,550 | 6,100 | 25,440 |
| Conduct monitoring and follow-up visits | 3,740 | 4,110 | 4,520 | 4,970 | 5,470 | 22,810 |
| Conduct program midterm and final evaluation (external) | 2,970 | 3,260 | 3,590 | 3,950 | 4,340 | 18,110 |
| Conduct network meetings and peer learning sessions through Alumni | 4,170 | 4,580 | 5,040 | 5,550 | 6,100 | 25,440 |
| Develop curriculum for Lydia's training | 630 | 690 | 760 | 830 | 920 | 3,830 |
| Distribute sewing machine for Lydia's ladies | 6,250 | 6,880 | 7,560 | 8,320 | 9,150 | 38,160 |
| Distribute hygiene kits for Lydia ladies and community women | 670 | 730 | 810 | 890 | 980 | 4,080 |
|  | 150,870 | 165,950 | 182,550 | 200,790 | 220,840 | 921,000 |