COUNTRY-LEVEL PROGRAM DOCUMENTATION

The entry point for the outcome-based approach will be a programme document which must be country specific with clearly defined objectives based on the approved outcome areas. The program document further outlines the inputs required (financial, technical, institutional, human and material resources) to produce the required outcomes.

SAMPLE PROGRAMME DOCUMENT

- GENERAL INFORMATION

| Title of the Program | International Needs Uganda Assistance Program (INUAP) |
| --- | --- |
| Location of the Program | Central and Eastern Districts of Buikwe, Mukono, Kayunga and Jinja |
| Program Duration | 5 Years |
| Start Date | 2023 |
| Completion Date | 2025 |
| Preparation Date | October 2022 |
| Program Budget |  |
| Contact Address | Plot 697, Kitakule Crescent, Off Balintuma Road – Mengo P.O. Box 7559 Kampala - Uganda |
| Telephone Number(s) | +256 392 612 570 +256 772 592 162 |
| Contact Email | info@inuganda.org justmiwanda@hotmail.com |
| Website (if any) | www.inuganda.org |
| Contact Person | Justus Miwanda |
| Designation | Executive Director |
| Contact Person’s Email | justmiwanda@hotmail.com |
| Program Focal Point | Ivan Muzanganda |
| Contact No. of Focal Point | muzangandaivan@gmail.com |
| - INTRODUCTION / BACKGROUND International Needs Uganda (INUG) is part of the global child focused Christian charity operating across 30 Countries to support development initiatives of vulnerable communities. It started as a Christian Youth mission in 1974 by Roy Harrison. The partnership focusses on holistic transformation of vulnerable Children, Women and Men. In Uganda, the ministry started in 1994 and was registered as a Non-Government Organization No. 3676 and with certificate of incorporation No. 56499 in 2003. INUG works with local, national and International partners to support development efforts of rural communities in Buikwe, Mukono , Kayunga, Wakiso, Iganga , Tororo and Jinja Districts since 1994. Our vision is To Glorify God and Win men, Women and Children for Jesus Christ and To connect Christian partners in effective evangelism, discipleship and community Development. INUG has been directly contributing to the wellbeing of over 200,000 lives annually. Lives have been transformed through interventions in OVC support, education, Agriculture, health, WASH and Christian nurture. INUG promotes access to education through Child Sponsorship. In Uganda, Children drop out or are absent from class for several reasons. Among poor families, the cost of school uniforms, books, stationery, and saving funds becomes too much to bear, pushing children out of school or leading families into debt. Illness and domestic work keep many children from attending school on a regular basis. Children with disabilities, orphans and other disadvantaged children are especially at risk of school exclusion UNICEF(2018) and so INUG has step up to reduce on this problem through the education programme we run. INUG Annually supports about 3620 children to access education out of which 2883 access education through the 3 INUG schools and 1337 through the partners schools in different places. This is achieved through partnership with the International Needs Global Partners, Local communities, other education institution and the Government. Through support from the development partners, there is continuous improvement in the education infrastructure and learning environment. We believe that all children have the right to have a good education and that education is vital to breaking the cycle of poverty. The long term aim is that these children will grow up with a solid, educational foundation that will enable them to gain employment in the future. The introduction is an initial pitch of the intended program. It sets the scene and tone for the general content of the document. This includes a description of the school / community, history of INAP in the school / community, the problem statement, statistical information, actions undertaken by various stakeholders in the past and present, organizational involvement and contributions. Indicate the current situation in the field of education in the community you want to work in. How many schools are there? How are school attendance rates? How is the education overall in the country you work in? Are there any specific reasons why you want to start or continue the assistance programme in the school or community? - STATEMENT OF NEEDS The right to education is one of the fundamental rights of a human being as stated in the Universal Declaration of Human Rights (1948). It is also recognized under various international and regional instruments to which Uganda is a party. The International Covenant on Social, Economic and Cultural Rights (1966) addresses, among other concerns, the right to education. It was ratified by Uganda in 1987. Likewise the Convention on the Rights of the Child (which Uganda ratified in 1990) deals with children’s rights including the right to education. It’s through education that marginalization and social-economic exclusion among OVC can be greatly reduced. In the case of Uganda, it is the Ministry of Education and Sports (MoES) that is charged with the responsibility of providing high quality education in the country at the lowest affordable cost and accessible to all and both the government and NGOs have made efforts over the years to improve access to formal education by introducing various policies like the Universal Primary Education. Measures have been put by the government of Uganda to improve access to education especially in public schools through the Universal Primary Education but accessing this education is a challenge for many communities. Universal Primary Education but accessing this education is a challenge for many communities.(Mpyangu, Ochen, Onyango and Lubaale 2014) in their study of “out of school children in Uganda” noted that Poverty stands out as the major reason which limits children from enrolling in school. The same study found out that Household poverty had a lot of repercussions on the child and the family where the child comes from and hence limiting their ability to stay in school. The same study conducted in 2014 found out that Household poverty had a lot of repercussions on the child and the family where the child comes from and hence limiting their ability to stay in school. In Jinja District and in particular in the 3 sub counties Parents are not able to make significant contributions towards the education of their children. Much as Parents of children in Buwenge Rural, Busedde and Butagayi make some contribution towards the education of their children, these contributions are modest considering the actual cost of providing quality education in these schools. Some children study on empty stomach because their parents can’t afford to pay for meals and this has a bearing on their level of concentration in class. The other associated problems in the community include; long distances the children move to school, high dependency burden due to low utilization of family planning services, illiteracy and ignorance, high child marriages, low income and power standard of living, child labour i.e girls are taken to work as maids in distant towns due to failure to frustration and boys work in sugarcane plantation at the expense of their education and high level of apathy. Therefore improving on improving on the lives of the community would require a holistic approach of empowering them to change their lives. Education would be the most appropriate intervention and hence a need for group assistance education programmme. Education would be the most appropriate intervention and hence a need for INCAP, INGAP and INSAP to support the children’s learning. - PROGRAMME STRATEGY A strategy is more about a designed set of options other than a fixed plan of what will be achieved. This generally communicates broad concepts or approaches to achieve the objectives of the programme. It outlines the detailed plan of actions designed to achieve a major or overall goal. INUG will partner with low income and vulnerable households in targeted rural communities in Buikwe, Mukono, Kayunga and Jinja Districts to identify, recruit and support orphaned and vulnerable children who would miss out going to school without external assistance. Targeted parents and guardians will elect community volunteers to work as Child protection Committee members/ Community based child monitors (CPCs/CBMs). The CPCs/CBMs will help in the identification, monitoring and providing regular information on the recruited children. The recruited vulnerable children who will be Under International Needs Child Assistance Program (INCAP) who be called participants will be linked to sponsors through International Needs Lead Partners for long term assistance with tuition, medical care, meals at School and Spiritual nurture from Pre-Primary to the end of Primary School level. Participants who will be able to enroll for Secondary level, Vocational or tertiary education will be under International Needs Students Assistance Program (INSAP). The will receive tuition, medical care, meals at their Schools and Spiritual nurture at a slightly higher value due to the high education costs at higher levels. The participants will access education at INUG Schools and other partner Schools and education Institutions. INUG will ensure that the participants access high quality education to help learner develop their full potentials to live meaningful life after School. Some of the participants will be placed under International Needs Group Assistance (INGAP). This category will be supported as groups and placed in the same education Institution (of either INUG or partner School/education Institution) for easy monitoring and reporting on their progress. INUG will also solicit for support for National workers; staff and Church Planters under International Needs Workers Assistance (INWAP). INUG will engage Support partners to fund key staff for a specialized function at INUG and Church leaders to evangelize and disciple unchurched communities through Church Planting activities. INUG will partner with selected Churches to identify and support Church planters. INUG will recruit child development Officers (CDOs) who will be in charge of between 300 to 400 participants to help them correspond to their sponsor, monitor, track and report their progress, provide regular psychosocial, moral and spiritual support among others. CDOs will closely work with CPCs, School teachers, parents and guardians to support participants under INCAP and INSAP to develop physically, intellectually, morally and spiritually. - PROGRAMME JUSTIFICATION According to Ministry of Gender, Labour and Social Development report on Orphans and other Vulnerable children (2017-18), Uganda faces a growing challenge of care and protection of Children, whose population is estimated at 19.03 million children below the age of 18 years. Of these children, 11 % have been orphaned and 44 % either critically or moderately vulnerable. These OVCs lack of security, are susceptible to risks and/or exploitation and without resilience to withstand shocks resulting from high levels of increased poverty at individual, households or community levels. Out of 8.5 million households in the country, 1.3 million had an orphan, constituting about 15 percent of all households. Overall, the total number of households with one orphan has slightly increased from 53 percent to 55 percent between the 2012/13 and 2016/17 survey undertakings. The OVC challenge cuts across the Country and deaths of the parents due to poor health system, separation of parents, single parents, shying away from responsibility by parents, abandoning of household members by bread winners among others. Attempts by the Government of Uganda over the years introduced UPE but still many OVCs can’t access education and the quality of education is lacking. INUG has over the past 20 years been supporting communities in Buikwe, Mukono and Kayunga to provide improved care for OVCs through INCAP. Over 5000 OVCs have been reached and supported to access quality pre-primary, Primary, secondary, Vocational and tertiary education and over 500 have graduated with various skills and profession and are engaged in meaningful/productive lives. However, there remains many more OVCs in various communities that INUG intends to reach out to especially in the eastern part of the Country with higher number of OVCs. The Proposed intervention will enable OVCs access improved care and support to in accessing education, health care, provision of physical needs and spiritual lives. There is moral decadency across many communities which has bread to violence, absence of peace, poor relationship among households and community members. INUG intends to support evangelism and discipleship among un churched communities to bring people to Jesus Christ. According to the Social Development Sector Plan (SDSP)-2015/16-2019/20; vulnerability relates to lack of security, susceptibility to risk and/or exploitation. It is a measure of resilience of individuals, households and communities to withstand any shock that might result in increased poverty. According to the findings at household level, the distribution of the number of orphans per household gives an insight of the magnitude of the problem for appropriate intervention. Out of 8.5 million households in the country, 1.3 million had an orphan, constituting about 15 percent of all households. Overall, the total number of households with one orphan has slightly increased from 53 percent to 55 percent between the 2012/13 and 2016/17 survey undertakings. On the other hand, those households with two orphans almost remained the same. At regional level, Karamoja sub-region had the highest proportion of households with four or more orphans (24%) compared to other sub-regions. (UNHS 2016/2017) Orphan hood in Uganda have been slightly on the decrease across the three survey periods from 15% (UNHS 2005/06) to 11% (UNHS 2016/2017). Orphan hood in female headed households was at 25% compared to male headed households at only 6%. The death of a father has been a major explanatory factor for orphan hood for the different background characteristics compared to death of a mother or both parents. Overall, a minimum of 2,048,000 (14%) of the children aged 5- 17 years were in child labour. The findings also show that, close to half of the old persons (42%) had never been to school and these were predominantly females (57%) compared to their male counterparts (23%).The majority of the widows (86%) were household heads implying they were major decisions takers in the household, and probably playing a lead role as well in looking after other household members. - PROGRAMME DESIGN Development objective: To improve the quality of life of vulnerable children, families and their households and partner communities by 2026 Specific objectives: - To support vulnerable children/ learners to access appropriate and quality primary, secondary, vocational and tertiary education for improved quality of life /quality living - To improve the quality of health and physical wellbeing of vulnerable children, young people and their households. - To support vulnerable children and young people to acquire life skills for effective decision making and responsible living. - To promote the gospel of Jesus Christ for spiritual formation and moral values among children, youths, women and men - To improve child sponsor relationships for long term commitment - To improve resource mobilization locally and globally for financing planned Assistance program/ interventions. Outcomes: - Improved application of knowledge and skills by young people by 2026 - Improved health and wellbeing of vulnerable children and their households - Improved meaningful participation of young people in their community development programs - Improved behavior and moral practices among children, families and communities that reflect Godly values - Increased and sustainable funding to support INUG Assistance programs Outputs - 6000 vulnerable children supported to access formal education and skills development. - Physical and Health wellbeing of 3000 sponsored vulnerable children and their guardians improved - Meaning full participation of 3500 young people in community development programs improved - The gospel of Jesus Christ promoted among children and partner communities - Improve child sponsor relationships for long term commitment. - Improve resource mobilization locally and globally for Assistance program/ interventions. Expected Activities and Description Education - Pay tuition for 3500 assisted children in school and other technical vocational centers - Provide scholastic materials for 400 highly vulnerable children - Work with schools and other vocational institutions to Provide meals to 6000 learners - Provide uniforms for 400 highly vulnerable children - Support 300 vulnerable girls with sanitary towels - Conduct school and home visits to monitor the education progress of supported children - Train teachers to provide career guidance and psychosocial support to learners - Support school with talking compounds for behavioral change communication - Support schools organize sports activities for talent development. Physical and Health wellbeing - Conduct health education sessions among sponsored children - Conduct health education sessions among care takers of sponsored children - Provide medical services to sponsored children through partners’ health facilities - Provide nutrition support to sponsored children with chronic conditions - Promote awareness creation among households of sponsored children on household income generation and food security - Conduct nutritional education among parents and guardians of sponsored children Life skills for effective decision making and responsible living - Support formation of health clubs in partner schools - Conduct career guidance and psychosocial support sessions among sponsored children - Liaise with partner schools to promote hands on skills development. - Conduct children debate sessions on key issues affecting their lives. The gospel of Jesus Christ promoted among children and partner communities - Conduct weekly school fellowships in schools - Conduct discipleship classes in schools - Conduct leadership sessions for scripture union clubs - Partner with local churches to conduct community evangelism and discipleship outreaches - Engage IN global partners to support church leaders for church planting among un churched communities Child sponsor relationships - Support children sponsor correspondence for a long term commitment to supporting Child assistance program - Recruit new participants in the assistance program - Develop and manage information management system for efficient storage and retrieval of participants’ information( The Link) - Develop staff capacity to manage Assistance program - Build capacity of community structures to support the Assistance program. - Promote child assistance through documentation of impact stories - Meaningful Sponsor Relations - Sustainable Funding and Administration |  |
| - PROJECT CROSS-CUTTING ISSUES CROSSCUTTING ISSUES Cross-cutting issues are topics that are identified as important and that affect and cut across most or all aspects of development. These will be integrated and mainstreamed throughout all stages of development from pogramme design, to implementation, evaluation and learning. Gender Analysis; Gender mainstreaming. The programme will always assess and include the concerns, experiences and the different implications for people of different gender in any planned programme intervention , in all areas and at levels so that women and men benefit equally and inequality is not perpetuated Gender equality. The programme will ensure that that women and men have the right to equal treatment, including the right to equal opportunities in social, economic, cultural, legal and social sphere. Principles of equality and non-discrimination are considered in our programme interventions. Therefore provisions will be made to ensure the involvement both men and women and the consideration of their issues in all processes, decision-making, and in implementation, monitoring and review of all decisions and service delivery.. Child Protection; Our programme (INUG INAP) believes in the fundamental rights of children and the need for children to grow up in a safe environment; giving them opportunity to enjoy a childhood that is free from exploitation and abuse. The programme therefore strives and is committed to ensuring safety in all aspects of our services to the children and like we take full responsibility to ensure establishment of systems that ensure protection of all children as well as supporting them to learn to embrace their responsibilities as children in a more balanced manner; as a way to ensure their holistic development. The programme will take full mandate to provide support to the staff, volunteers, contractors, care takers and visitors about acceptable behavior and actions towards children during their direct and indirect contact with children while working with INUG. Child Protection Policy provides a strong foundation for all of us including our partners by setting the standard for our staff both on duty and off duty to exhibit behaviors that are expected of International Needs Uganda towards children.. Disability Inclusion; Knowing that Persons with disabilities are more likely to experience adverse socioeconomic outcomes than persons without disabilities, such as less education, poorer health outcomes, lower levels of employment, and higher poverty rates, the programme will support efforts that will ensure that persons with disabilities can fully participate in and have access to services such as education, health and life skills. The INAP document will also ensure that Persons with disabilities are involved and represented in all stages of the programme cycle. The programme will also ensure that inequalities between disabled and non-disabled persons are addressed in all the strategic areas of our work.. Family Planning; Family planning being a critical aspect in community development and transformation. Our programme will promote adaptation of voluntary family planning in all our areas of operation in terms of practices, information and building attitudes that give women, men, couples, and adolescents the ability to avoid unintended pregnancy and choose whether and/or when to have a child and how often should they have a child. The programme will majorly linking them to service providers and conduct education programme on the available family planning services and where they can be accessed.. HIV and AIDS; People living with HIV often live in fragile communities and are frequently discriminated against, marginalized and affected by inequality. Where necessary, the programme will provide or link people affected and infected with HIV to facilities where they can be supported emotionally, spiritually, psychologically, social, physically and medically. E.g providing nutritional health education to enable families to improve their diets using cheap and available foods , providing Counseling services to reduce isolation and promote acceptance , Spiritual support such as prayer groups and home visits by religious leaders, provide information for its members so that they can understand the disease and be able to educate their family members, friends, colleagues, neighbours about the disease.. RISK MANAGEMENT PLAN This plan tells how to deal with specific risks and what management actions must be taken against those risks to mitigate or remove threats to the programme tasks and outcomes. The risk management plan gives all stakeholders a sense of measures they need to take to identify, analyze, and respond to all the risks running around within the programme wheel. This Risk Management Plan documents the processes, tools and procedures that will be used to manage and control risk events that could have a negative impact on the INAP. It’s the controlling document for managing INAP risks. This plan will address: - Risk Identification - Risk analysis-Cause & Nature of the risk - Risk Assessment-Likely hood of occurrence and Impact - Risk Response-Prevention, Acceptance, Avoidance, Reduction, Transfer, Mitigation, Deference - Risk Mitigation- - Risk Monitoring and control Many of these processes will be updated throughout the project lifecycle as new risks can be identified at any time. It’s the purpose is to decrease the probability and impact of events adverse to the project. On the other hand, any event that could have a positive impact should be exploited. The process was conducted by the INAP project manager together with the project team to ensure that a wide range of risks are covered as tabulated in the risk management plan below; Key and Ranking levels and L-Likelihood (Almost Certain, Likely, Possible, Unlikely, Rare) C-Impact (Catastrophic, Major, Moderate, Minor, Insignificant) R-Risk Level (Extreme, High, Moderate, Low) Likelihood of occurrence Vis-à-vis the impact if it occurred. Risk Management Plan Risk Event; Likelihood of occurrence; Risk revel; Risk Impact; Risk Response; Risk Mitigation; Risk Monitoring & Control; Person Responsible. Provision of inaccurate and false information by caregivers of potential beneficiaries; Possible; Moderate; Major; Prevention; -Strengthen capacity of duty bears to verify information and make accurate assessments before selecting the beneficiaries.; -Conduct pre & Post case record verification exercise; Sponsorship Manager. Weak law enforcement on child rights abuses; Likely; High; Major; Reduction; -Strengthen referral links & Networks -Organize advocacy programs for Community members.; -Track child protection cases concluded -Review case management records.; Human Resource Manager. Sponsorship Manager.. Inappropriate sponsor-child communication through social media misuse.; Possible; High; Moderate; Reduction; Strengthen compliance to the child sponsorship and child protection policy; IMS review INUG Child Protection Policy review; Sponsorship Manager, ED and Human Resource Manager. Child Assistance sponsor cancellation; Likely; High; Major; Reduction; Build partnerships with other potential sponsors; Reviewing partnership agreements; Executive Director. Sponsorship Manager. Participants relocation out of the program area; Likely; Moderate; Major; Reduction; Enroll participants whose households are stable; Review the child selection criteria; Sponsorship Manager. Station heads.. High commodity prices; Likely; High; Major; Mitigation; Make the procurement process more competitive and selection of bidders with the lowest price offers; Review supplier agreements and terms of references; Procurement committee. Programme partners not being committed to the terms of partnership; Rare; High; Major; Prevention; Vetting the partners and dealing with reliable programme partners; Review of MOUs and strengthen compliance; Executive Director HRM Programme Manager. Miss use of project resources by staff and communities; Rare; High; Catastrophic; Prevention; Strengthen and update the internal control systems to detect and respond to issues of resource misuse.; Regular and routine monitoring of the organization’s resource usage.; Executive Director. Finance and Audit department.. High community expectations and over reliance on the programme; Likely; High; Moderate; Reduction; Increase community participation and engagement so that they can own the programme interventions; Conduct dialogue and community engagement meetings to harmonize each other’s expectations.; Sponsorship Manager. Community Volunteers. Double sponsorship; Rare; Moderate; Moderate; Reduction; Networking and sharing of information with other agencies; Regular review and update of participants’ information.; Sponsorship Manager. Data officer.. - MONITORING AND EVALUATION PLAN INTERNATIONAL NEEDS UGANDA ASSISTANCE PROGRAM (INUAP) MONITORING AND EVALAUTION PLAN (2021-2024). Organization Name:; INTERNATIONAL NEEDS UGANDA. Project Name:; INAP. Project planning Period:; Jan 2023 – Dec 2025. Impact, Outcomes and Outputs; Indicators.; What type of data needs to be collected?; What are the data sources?; What tools will be used to collect data?; How often is data to be collected?; Who collects data?. Goal: To improve the quality of life of 6000 vulnerable children, families, their households and partner communities by 2026; % improvement of lives of OVCs; Data of OVC enrolled in the program and served; End of Program Evaluation report; Questioners; Midterm and End term; External evaluator. % improvement of lives of OVCs households among partner communities; Data of OVC enrolled in the program and served; End of Program Evaluation report; Questioners; Midterm and End term; External evaluator. Outcome 1: Improved application of knowledge and skills by young people by 2026; % increase in Children completing primary, Secondary and Vocational schools.; Data on enrolment and completion; Enrolment reports, final assessment reports; Academic reports; Termly; INUAP team. No of youth with gainful employment after graduating from vocational institute; Data on IGA initiated by youth; Activity Monitoring tools. Outcome 2: Improved health and wellbeing of vulnerable children and their households; No of Children, their households and partner communities reached with health services. No of households with stable IGAs(Income generation Activities) that are food secure and able to meet nutritional needs of their members. Outcome 3: Improved meaningful participation of young people in their community development programs; Sponsored children whose skills are built to manage life challenges. No of children actively participating in community development programs(Child Advocacy, Youth livelihood). Outcome 4: Improved behavior and moral practices among children, families and communities that reflect Godly values; No of people reached with the Gospel of Jesus Christ. No of people converting/ accepting Jesus Christ as their Lord and Saviour. No of believers nurtured in Christian living. Outcome 5: Increased and sustainable funding to support INUG Assistance programs; No. of grant sponsored children accessing Education (primary, secondary and vocational), health, nutrition, advocacy and child rights, Spiritual development and life skills. No of partners with signed MoUs supporting the OVC activities spearheaded in Assistance program. No of quality correspondences between sponsored children and their sponsors submitted in time. Availability of functional records management system/ data base developed for Assistance program. No of Child Protection Committees (CPCs) with strengthened advocacy skills to create community awareness and engage local authorities on OVC care and protection. No of OVC accessing education, health care, spiritual, moral nurture and career guidance through child sponsorship. Output 1: To improve application of knowledge and skills of 6000 young people by 2026; Number of Children completing primary, Secondary and Vocational schools.. Number of children able to apply acquired knowledge and skills to improve their livelihood. No of youth with gainful employment after graduating from vocational institute. Output 2: To improve health and wellbeing of 3860 vulnerable children and their households; No of Children, their households and partner communities reached with health services. No of households with stable IGAs(Income generation Activities) that are food secure and able to meet nutritional needs of their members. Output 3: To improve meaningful participation of 6000 young people in their community development programs; Sponsored children whose skills are built to manage life challenges. No of children actively participating in community development programs(Child Advocacy, Youth livelihood). Output 4: To improve behavior and moral practices among 6000 children, their families and communities that reflect Godly values; No of people reached with the Gospel of Jesus Christ. No of people converting/ accepting Jesus Christ as their Lord and Saviour. No of believers nurtured in Christian living. Output 5: Increased and sustainable funding to support INUG Assistance programs targeting 3860; No. of grant sponsored children accessing Education (primary, secondary and vocational), health, nutrition, advocacy and child rights, Spiritual development and life skills. No of partners with signed MoUs supporting the OVC activities spearheaded in Assistance program. No of quality correspondences between sponsored children and their sponsors submitted in time. Availability of functional records management system/ data base developed for Assistance program. No of Child Protection Committees (CPCs) with strengthened advocacy skills to create community awareness and engage local authorities on OVC care and protection. No of OVC accessing education, health care, spiritual, moral nurture and career guidance through child sponsorship. - PROJECT ACTIVITY SCHEDULE An activity schedule is an analytical tool for graphically presenting and reviewing the activities of a project. It helps to identify the logical sequence of the activities, estimate their duration, and denote any dependencies that exist between them. The activity schedule also serves as a foundation for allocating management authority and responsibility. Typically, the columns must capture a list of all activities with timelines and persons responsible. Objective/Activities; Year One; Year Two; Year Three; Year Four; Year Five. Objective: 1 To support vulnerable children/ learners to access appropriate and quality primary, secondary, vocational and tertiary education for improved quality of life /quality living. Activity 1.1: Pay tuition for 3500 assisted children in school and other technical vocational centers. Activity 1.2: Provide scholastic materials for 400 highly vulnerable children. Activity 1.3: Work with schools and other vocational institutions to Provide meals to 6000 learners. Activity 1.4: Provide uniforms for 400 highly vulnerable children. Activity 1.5: Support 300 vulnerable girls with sanitary towels. Activity 1.6: Conduct school and home visits to monitor the education progress of supported children. Activity 1.7: Train teachers to provide career guidance and psychosocial support to learners. Activity 1.8: Support school with talking compounds for behavioral change communication. Activity 1.9: Support schools organize sports activities for talent development. Objective: 2 To improve the quality of health and physical wellbeing of vulnerable children, young people and their households.. Activity 2.1: Conduct health education sessions among sponsored children. Activity 2.2: Conduct health education sessions among care takers of sponsored children. Activity 2.3: Provide medical services to sponsored children through partners’ health facilities. Activity 2.4: Provide nutrition support to sponsored children with chronic conditions. Activity 2.5: Promote awareness creation among households of sponsored children on household income generation and food security. Activity 2.6: Conduct nutritional education among parents and guardians of sponsored children. Objective: 3 To support vulnerable children and young people to acquire life skills for effective decision making and responsible living.. Activity 3.1: Support formation of health clubs in partner schools. Activity 3.2: Conduct career guidance and psychosocial support sessions among sponsored children. Activity 3.3: Liaise with partner schools to promote hands on skills development.. Activity 3.4: Conduct children debate sessions on key issues affecting their lives. Objective: 4 To promote the gospel of Jesus Christ for spiritual formation and moral values among children, youths, women and men. Activity 4.1: Conduct weekly school fellowships in schools. Activity 4.2: Conduct discipleship classes in schools. Activity 4.3: Conduct leadership sessions for scripture union clubs. Activity 4.4: Partner with local churches to conduct community evangelism and discipleship outreaches. Activity 4.5: Engage IN global partners to support church leaders for church planting among un churched communities. Objective: 5 To improve child sponsor relationships for long term commitment. Activity 5.1: Support children sponsor correspondence for a long term commitment to supporting Child assistance program. Activity 5.2: Recruit new participants in the assistance program. Activity 5.3: Develop staff capacity to manage Assistance program. Activity 5.4: Develop and manage information management system for efficient storage and retrieval of participants’ information. Activity 5.5: Build capacity of community structures to support the Assistance program. Activity 5.6: Promote child assistance through documentation of impact stories. - PROGRAMME BUDGET The project budget describes the monetary aspects of the project and explains exactly, which areas of how much money should be spent. A project budget simply refers to a document that specifies how the money will be allocated to implement the activities described in the proposal. |