INAP PROGRAMME DOCUMENT

- GENERAL INFORMATION

| Title of the Program | International Needs Zambia Assistance Program (INZAP) |
| --- | --- |
| Location of the Program | ZACTS – (Solwezi), Misaka – (Luanshya), Emele – (Masaiti) |
| Program Duration | 5 Years Program |
| Start Date | January 1, 2023 |
| Completion Date | December 31, 2027 |
| Preparation Date | November 11, 2022 |
| Program Budget | US $4,573,844.68 (ZMK68,307,670.20) |
| Contact Address | International Needs Zambia Kimasala – Mulenga Road, Muzabula Area P O Box 110127, Solwezi – Zambia |
| Telephone Number(s) | +260 977500748, +260 968840054 |
| Contact Email | zactsovcschool@gmail.com |
| Website (if any) | None |
| Contact Person | Warren M Nyimba |
| Designation | Executive Director |
| Contact Person’s Email | warrenmnyimba@gmail.com |
| Program Focal Point | Rev. Jibusha Eddie Maunga |
| Contact No. of Focal Point | +260 977500748 |
| - INTRODUCTION / BACKGROUND International Needs Zambia (INZM) was established in 1984. This program was based on biblical scripture, James 1:27 which talks about pure and undefiled religion that God is pleased with. It is beyond doubt that education is the key to poverty alleviation, improved behavior and sustainable development. In view of this IN Zambia has three ministries in two provinces; ZACTS in Solwezi, North Western Province and Misaka Home Based Care in Luanshya and Emele Memorial School in Masaiti on the Copperbelt Province of Zambia. The extent of hunger and extreme poverty situation in these communities around our ministries triggered the desire to help the helpless. Before INZM came into the program the communities were unable to send their children to school due to failure to provide money for school fees, uniforms and other requirements. Therefore, 70% of their children had no access to education, compelling INZM to embarked on the identification of these less privileged children in the nearby communities where the schools were situated. At the commencement of the program, the first activity in 1984, ZACTS identified Lay Preachers in order to equip them with Christian values and Life skills that would enable them preach God’s word while they could support themselves from their agricultural activities. This program was being supported by INUK, INUS. The program was successful for a period of about 6 years, and another activity was instituted. In the second activity ZACTS identified young men and women within and outside the communities to be trained in Biblical studies and sustainable life skills, such as General Agriculture, Home Economics, Hotel management, and Carpentry. This program was being supported by INUS, INNZ, INAU. The program was also successful for 20 years until it ended due to a shift of ministry. Then another program was introduced in 2011, and this was about introducing an academic education for the less privileged children who had no chance to find places in government schools due to the demise of their parents, which resulted to non-availability of education support. ZACTS identified 60 OVCs to commence their Pre-school education with the support from IN Canada. While Misaka HBC and Emele school identified 30 OVCs each. All the programs were being assisted through INCAP with sponsors from INCA, INUS and INUK. The current situation in the field of education in the communities where INZM is involved is very worrying. This is because free education policy has led to increased enrollment, thereby multiplying the number of pupils to almost double for example, at the end of December 2021, ZACTS school had a total number of 700 but early this year the number has increased to 1,200. Thus, there is now need for more staff houses, classroom blocks and teachers. Furthermore, in the agricultural sector there was low production despite having arable land and some farming machinery. There is therefore need to have funds to support agricultural enterprises. Therefore, INZM is grateful to God for International Needs Incorporated for the idea of coming up with a program document that will enable this organization to share the activities that will be undertaken for the period 2023 to 2027. The other segment is on water supply and sanitation that has become inadequate due to increased population and other activities. There is need to improve on sanitation facilities. So, this five-year program document brings out: - The background and the development of the INZM, - The needs of the organization, the strategy of the program and its justification, - The design of the program, cross-cutting issues, risk management and monitoring and evaluation plans, and - The project activity schedule and the needed program budget. We are therefore humbly seeking support in fulfilling the global goal of transformed lives and changed communities. - STATEMENT OF NEEDS INZM is facing a big challenge in running ZACTS OVC, Emele Memorial Schools and Misaka Home Based Care due to inadequate funding. The ministry of ZACTS OVC is receiving assistance for 170 pupils through INCAP and estimated 62 pupils through INGAP. Thus, the funds for 232 beneficiaries are covering for the 968 pupils who are not assisted. The ministries of Misaka & Emele are receiving assistance through INCAP for 72 and 18 pupils respectively. The rapid increase of the school enrolment has increased the needy areas as stated below: - increased feeding program, - increased daily monitoring activities, - increased classroom space, - increased accommodation for teaching staff, especially teachers seconded to the school from government, - increased water reticulation, and - increased sharing of the gospel of Jesus to all school pupils. Urgent issue at hand is that all workers who were employed on contract are supposed to be paid the gratuity packages, but this has not been done due to the fact that INWAP was not fully implemented in INZ. Nevertheless, we are improving on fundraising ventures to supplement what IN Incorporated is giving us. - PROGRAMME STRATEGY This program is designed in order to give hope to the hopeless by providing free quality education, basing on the scripture, Luke 2:52. Thus, we envisage every child being reached, to grow as our Lord Jesus grew in four areas; first in Wisdom which is linked to the outcomes of educational development. Second area is Stature – which is linked to physical and health development. Third area is Favor with God – which is linked to the Spiritual development through sharing the word of God. The fourth area is Favor with Men – which is linked to the Social development while looking at value formation. Therefore, IN Zambia becomes a link between the partners and the beneficiaries, whose task is to mobilize resources and implement the program according to the laid down procedure. In order to achieve these strategies, IN Zambia has put in place the following Leadership: - INZM Board of Directors – to formulate and regulate policies - Executive Director – to oversee the implementation of activities - Senior Project Coordinator – dealing with Assistance Program and creation of projects that will bring about transformed lives and changed communities, - Business Administrator – dealing with staff & finances, - Head teacher – overseeing the education program, and - Farm Manager – managing all farming activities - PROGRAMME JUSTIFICATION Currently, IN Zambia’s passion is to continue working with the same communities in the Copperbelt and of Muzabula and Kambeu in Solwezi because there are so many children who have the desire to learn as seen from the numbers which have increased from 700 in 2021 to 1,200 in 2022. Having this program in place will provide guidance in performing the duties required, and will also provide partner support in running the ministry with minimum challenges, as we look forward to achieve the needed outcomes. - PROGRAMME DESIGN - Development Objective: To ensure inclusive & equitable quality education & promote life-long learning opportunities to OVCs by 2027. - Specific Objectives: - To improve quality education by providing qualified teaching staff. - To provide/construct enough classroom space - To provide quality health and physical wellbeing of vulnerable children, young people, community women and their households. - To support Orphaned and Vulnerable Children / young people to appropriate primary, secondary, vocational and tertiary education. - To mobilize resources locally and globally for financing planned Assistance Programs. - To promote the gospel of Jesus Christ. - To improve child - sponsor relationships. - To empower the communities with fund raising ventures. - To identify yardsticks for measurement - Expected Outcomes (educational, life skills and social development, physical and health, spiritual and value formation) - Improved application of knowledge and skills by young people by 2027 - Improved classroom space - Improved health and wellbeing of vulnerable children and their households - Increased and sustainable funding to support INZM Assistance programs - Improved behavior and moral practices among children, families and communities that reflect Godly values - Improved child sponsor relationships for long term commitment. - Improved meaningful participation of vulnerable young and adult women in their community development programs - Expected Outputs - Provision of quality education improved, 30 qualified teachers trained - 3 x 3 classroom blocks constructed to provide enough space to growing number of pupils. - Health center (school clinic) constructed and Physical and Health well-being of all school pupils and their guardians improved. - 2,000 OVCs supported to access free quality education and skilled development. - Resource mobilization for assistance programs locally and globally improved. - The Gospel of Jesus Christ for behavioral change and value formation promoted among the school pupils. - Child-sponsor relationships improved - Vulnerable Community people empowered with income generating ventures. - Expected Activities and Description Activity; Description of the Activity. Physical and Health development. 1; Establish a school clinic, hire workers and procure drugs at ZACTS OVC School.; Renovating the existing building for a clinic. 2; Provide sanitary pads for all girls from grade 5 to grade 12 in all ministries; Promoting Female pupils’ hygiene. 3; Provide feeding program for 2,500 children in 3 ministries for five years; INGAP to support the program. 4; Organize bi-annual medical outreaches at ZACTS; Medical Team visits Through INCAP support. 5; Provide clean and potable water supply – 1 for school and 3 for the community.; Drilling of boreholes. Educational development. 1; Procure teaching and learning materials for ZACTS and Emele; For Teachers & Learners’ use. 2; Hold quarterly Continued Profession Development (CPD) sessions for teachers.; School in-service training. 3; Provide school uniforms for sponsored pupils only; All grades with assisted pupils. 4; Enroll 100 pupils in Emele and ZACTS schools each year; November enrolments. 5; Organize study trips for students at ZACTS, Misaka and Emele; Educational Tours. 6; Pay wages for volunteer teachers at ZACTS and Emele; Motivation & upkeep. 7; Support for 96 INSAP participants; College Students. 8; Support INGAP participants in school; 650 Primary pupils & 430 Secondary pupils. 9.; Procure Home Economics Utensils; H E Classes equipment. 10; Procure 40 computers to support ICT Studies; For Computer Laboratory. Life Skills and Social development. 1; Form and support a tailoring club for young mothers who have dropped out of school.; 1-year Empowerment program (INGAP). 2; Form and support a 10 women cooperative group that will be empowered through agricultural program each year.; Community empowerment program. 3; Organize sporting activities for pupils at ZACTS and Emele.; School co-curricular activities. 4; Procure sports equipment for sporting activities at ZACTS and Emele; Sports attire & equipment. 5.; Enhance school Agricultural Activities; School production Unit. Spiritual development and Value formation. 1; Form and provide Spiritual and Biblical materials to a Bible group of 200 pupils at ZACTS, Misaka and Emele.; Provide biblical materials. 2; Form Evangelism and Counselling Ministry; Outreach ministry. Infrastructure development. 1; Construct 4 by 3 classroom blocks at ZACTS & Emele; Creation of classroom space. 2; Construct 4 by 4 blocks of staff flats at ZACTS & Emele; Staff Accommodation. 3; Construct 2 ablution blocks for students in primary and secondary school at ZACTS and 1 block for Emele; Water-bone toilets. 4; Maintain furniture, classroom blocks, houses and offices; Repair works. 5; Construct 1x4 Farm Office Block; Farm Manager, Assistant & Workers’ offices. 6; Input Storage Shed for Farming; Storage for agricultural inputs. 7; Construct Grain Storage; Cereal and grain crops. 8; Construct Warehouse; Tools & Equipment Storage. 9; Construct Piggery House; Rearing of pigs. 10; Construct 4 Farm Dwelling House; Workers’ Accommodation. 11; Construct Poultry Security Wall; Restrict unnecessary entries & avoid poultry diseases. Administrative Activities. 1; Pay for employees’ benefits; 35 employees. 2.; Pay salaries and wages for INWAP participants; 4 INZM staff. 3; Capacity Building for Workers in all sectors of ministry; In-service training for workers. 4; Purchase a utility vehicle; For Ministries operations. 5; Maintain quarterly reporting for all activities; Pupils’ letter writing and Project Reports. 6; Pay for administrative costs; Utility bills, fuel and lubricants, stationery and other office requisites. - Target Groups / Clientele The following are the target groups that INZM wishes to seek and provide support for the well-being of their lives, if these lives are transformed then even the community will change; - Teachers that are employed to impart knowledge in our pupils should be of quality. - Unassisted pupils should find assistance in order to ease the feeding program. - Vulnerable women of the community, who are also parents and guardians of our children. - Young mothers within the community who have stopped school due to pregnancies. - School children at ZACTS need frequent medical attention first before the community people. - Unbelieving school pupils whose behavior is unruly. - Meaningful Sponsor Relations From the onset of sponsorship program, there has been a good relationship between the sponsor and the sponsored child, including the staff connected with the sponsorship program. As long as the child completes his or her education the relationship will never end and will appreciate God for the extension of his love through sponsorship. - Sustainable Funding and Administration The following are the measures put in place to sustain funding: - INCAP, INWAP, INGAP, INSAP, - Local income generating enterprises - Grants from Zambia Open Community Schools (ZOCS) - Grants from Government of the Republic of Zambia (GRZ) - Donations and gifts from well-wishers - Support from Corporate Social Responsibility (CSR) The funds will be administered by a competent management team that will ensure: - adherence to accounting procedures and processes - adherence to rules and regulations to guide funding utilization - external Audits are conducted |
| 7. PROJECT CROSS-CUTTING ISSUES - Gender Analysis INZM has mainstreamed gender in the organization in that out of six Board members, three are women and three are men. The school has a deliberate policy to promote women and girls. For instance, the teaching staff has majority women teachers and the school enrolment has more girls than boys. The school has a gender focal point person to coordinate gender activities at the school. 7.2 Child Protection INZM did put in place a child protection policy which protects the child from the evil hands of the abuser. Each new teacher we employ receives a copy of the policy which should be read and signed in conformity with national policy, a signed copy is filed on the teacher’s personal file. - Disability Inclusion ZACTS OVC school is aware of the challenges of people with disabilities accessing buildings. For instance, the current 1 x 2 classroom block put up a sliding floor and not steps alone. Plans are under way to put up sliding floors on all buildings. In fact, the school has a disabled child with a shorter leg. - HIV/AIDS INZM, represented by the Senior Project Coordinator, has been a stakeholder with District Task Force for HIV/AIDS council. INZ has been doing sensitization programs during school open day gatherings. This program tends to continue since it provides a link between the community people affected and infected with HIV to facilities where they can be supported emotionally, spiritually, psychologically, social, physically and medically. E.g. providing nutritional health education to enable families to improve their diets using cheap and available foods, providing Counseling services to reduce stigma and promote acceptance. Spiritual support such as prayer groups and home visits by religious leaders, also provide mitigation. 8. RISK MANAGEMENT PLAN Risk Identification; Risk Assessment; Risk Mitigation; Risk Monitoring; Person Responsible. Child Rights Abuse; High; Organize advocacy programs for community members and teaching staff; Conduct pre-& Post case record verification cases on rights abuse.; Headteacher & PTA members. Misuse of funds; Low; Strengthen the internal controls.; Review case management records. Auditing of accounting records; Business Admin. & Procurement officer. Fire; Moderate; Carry out fire risk assessment daily. Ensure good housekeeping rules at all times.; Assess fire risk cases; Maintenance officer Stores man & Truck drivers.. Diseases; Moderate; Provide Nutritious Food Enhance Physical Activity Ensure Clinical Checkups; Review cases of in and out door diseases; Clinical officer & Kitchen staff. Pupils’ relocation; High; Enroll pupils whose households are stable. Organize follow-ups; Review the child selection criteria; Sponsorship Manager. Headteacher. High commodity prices; High; Organize procurement based on market pricing. Apply financial hedging Use long-term supply contracts; Review supplier agreements and terms of references; Business Admin & Procurement committee. Theft of project materials; Moderate; Strengthen security systems; Review cases of theft; Executive Director, Snr Project Coordinator & Security men.. Child Early pregnancies & marriages; High; Strengthen advocacy programs. Allow law enforcement officers to control the situation.; Review cases of pregnancies and early marriages.; Executive Director. Snr Project Coordinator & Headteacher. Being sued for non-payment of staff gratuity and other terminal benefits.; High; Open reserve account for workers’ gratuity & other benefits Liaise with our partners for possible support; Ensure adherence to the conditions of service.; Executive Director & Business Admin.. Pupils’ school injuries; High; Ensure safety are put in place Ensure Regular teacher monitoring system; Review cases of injury during school time; Headteachers & Class teachers.. - MONITORING AND EVALUATION PLAN. Development Goal: Ensure inclusive & equitable quality education & promote life-long learning opportunities for all.. ACTIVITIES; INDICATOR (s); BASELINE; TARGET; FREQUENCY (How often will it be measured?); MEANS OF VERIFICATION; RESPONSIBLE; REPORTING. What is the current value?; What is the target value?; Year 1; Year 2; Year 3; Year 4; Year 5; Who will measure it?; Where will it be reported?. 01.Establish a school clinic, hire of workers and procure drugs and sanitary pads for ZACTS OVC pupils.; Number of pupils & staff workers.; 1,223; 2,500; 4x; 4x; 4x; 4x; 4x; Maintain records of patients being attended to; Snr Project Coordinator & Clinical staff; Quarterly Project Reports. 02.Enhance feeding program for 2,500 children in 3 ministries; Number of assisted participants being fed.; 2,500; 2,500; 4x; 4x; 4x; 4x; 4x; Records in the Kitchen store room; Business Administrator/ Head Teacher; Quarterly Project Report. 03. Provide clean and potable water – 1 for school and 3 for the community.; Number of boreholes drilled.; 4; 4; weekly; weekly; weekly; weekly; weekly; Visit borehole sites; Executive Dir./ Snr Project Coordinator; Quarterly Project Report. 04. Organize by-annual medical outreaches in ZACTS; Number of medical team visits from Canada; 3; 3; Monthly; Monthly; Monthly; Monthly; Monthly; Record of the visits; Snr Project Coordinator; Quarterly Project Report. 05. Procure teaching and learning materials and school uniforms sponsored pupils for ZACTS and Emele; Number of materials being provided; 60%; 100%; daily; daily; daily; daily; daily; Records of procurements; Deputy Head/ Procurement officer; Quarterly Project Report. 06 Uphold quarterly Continued Profession Development (CPD) sessions for teachers.; Number of CPD meetings held; 23; 30; weekly; weekly; weekly; weekly; weekly; CPD attendance records; Headteacher; Quarterly Project Report. 07. Uphold support for INCAP participants, also mobilize support for INSAP, INGAP and INWAP.; Number of participants on these programs.; 2,500; 2,500; 4x; 4x; 4x; 4x; 4x; Records of participants; The Project Coordinator and the ED; Quarterly Project Report. 08. Organize educational trips for students at ZACTS, Emele and Misaka; Number of trips undertaken; 07; 12; termly; termly; termly; termly; termly; Teachers and Leaners happily using the materials; The deputy head; Quarterly Report. 09. Procure 40 computers (compulsory ICT studies) and Utensils for HE Classes; Number of computers & utensils purchased; 12; daily; daily; daily; daily; daily; Record of learners acquiring knowledge; The Business Administrator & Project Coordinator; Quarterly Project Report. 10. Form and support a tailoring club for young mothers who have dropped out of school.; Number of young mothers trained; 10; 50; Quarterly; Quarterly; Quarterly; Quarterly; Quarterly; Record of trained young women; Snr Project Coordinator; Quarterly Project Report. 11. Form and support a 10 women cooperative group that will be empowered through agricultural program.; Number of women grouped; 10; 50; Seasonal; Seasonal; Seasonal; Seasonal; Seasonal; Record of women participating; Farm Manager & Board member; Quarterly Project Report. 12. Enhance school Agricultural Activities (ZACTS 7 Misaka Farms).; Number of Farm activities enhanced; 03; 03; 4x; 4x; 4x; 4x; 4x; Record of farm products; Farm Manager & Headteacher; Quarterly Project Report. 13. Form and provide Biblical materials to a Bible group of 200 pupils at ZACTS, Misaka and Emele.; Number of participants joining the group; 50; 200; Weekly; Weekly; Weekly; Weekly; Weekly; Record of meetings; Snr Project Coordinator; Quarterly Project Report. 14. Form Evangelism and Outreach/ Counselling Ministry; Number of people counselled; 100; 500; Monthly; Monthly; Monthly; Monthly; Monthly; Record of those Evangelized & Counselled; Snr Project Coordinator & School Guidance & Counselling; Quarterly Project Report. 15. Construction of school classroom, staff houses, and ablution blocks.; Number of blocks constructed; 06; 09; Weekly; Weekly; Weekly; Weekly; Weekly; Record of buildings constructed; Snr Project Coordinator & the ED; Quarterly Project Report. 16. Maintain quarterly reporting of all activities; Number of reports submitted; efficient; More efficient; 4x; 4x; 4x; 4x; 4x; Record od reports submitted; ED, SPC & Dept Heads; Quarterly Project Report. 17. Capacity Building for Workers in all sectors of ministry; Number of trainings held; Essential Workers; All Workers; 2x; 2x; 2x; 2x; 2x; Record of workers trained; ED, SPC & BA; Quarterly Project Report. - PROJECT ACTIVITY SCHEDULE Activity; Year 1 (2023); Year 2 (2024); Year 3 (2025); Year 4 (2026); Year 5 (2027). #; Q1; Q2; Q3; Q4; Q1; Q2; Q3; Q4; Q1; Q2; Q3; Q4; Q1; Q2; Q3; Q4; Q1; Q2; Q3; Q4. Physical and Health development. 1; Establish a school clinic, hire of workers and procure drugs at ZACTS OVC School.. 2; Provide sanitary pads for all girls from grade 5 to grade 12 in all ministries. 3; Enhance feeding program for 2,500 children in 3 ministries. 4; Organize by-annual medical outreaches in ZACTS. 5; Provide clean and potable water – 1 for school and 3 for the community.. Educational development. 1; Procure teaching and learning materials for ZACTS and Emele. 2; Uphold quarterly Continued Profession Development (CPD) sessions for teachers.. 3; Provide school uniforms to sponsored pupils. 4; Enroll at least 100 pupils in two schools each year. 5; Organize educational trips for students at ZACTS, Emele and Misaka. 6; Motivate volunteer teachers at ZACTS and Emele with allowances. 7; Uphold support for INCAP participants. 7; Support for 96 INSAP participants in school. 8; Support for 650 INGAP Primary participants. 9; Support for 430 INGAP Secondary participants. 10; Procure Home Economics Utensils. 11; Procure 40 computers (compulsory ICT studies). Life Skills and Social development. 1; Form and support a tailoring club for young mothers who have dropped out of school.. 2; Form and support a 10 women cooperative group that will be empowered through agricultural program.. 3; Organize sporting activities for students at ZACTS & Emele. 4; Procure sports equipment for sporting activities in ZACTS and Emele. 5.; Enhance school Agricultural Activities (ZACTS & Misaka Farms). Spiritual development and Value formation. 1; Form and provide Biblical materials to a Bible group of 200 pupils at ZACTS, Misaka and Emele.. 2; Form Evangelism and Outreach/ Counselling Ministry. Infrastructure development. 1; Construct 4 by 3 classroom blocks at ZACTS and Emele. 2; Construct 4 by 4 staff flats at ZACTS and Emele. 3; Construct 2 ablution blocks for students in primary and secondary school at ZACTS and 1 block for Emele. 4; Maintain school furniture, classroom blocks & houses. 5; Construct 1 x 4 farm office block. 6; Input storage shed for farming. 7; Construct Grain storage. 8; Construct Ware house – tools & equipment. 9; Construct piggery house. 10; Construct 4 farming dwelling houses. 11; Construct poultry Security wall. Agricultural Programs. 1.; Provide inputs for ground nuts, soya beans, sunflower and maize. 2; Procure fruit trees and their inputs (oranges, Lemons, Guavas, paw paws and Mangoes). 3; Provide inputs for broiler, layers, Rabbits, Ducks, Pigs and Cattle rearing.. 4; Pay salaries for Agricultural Employees. Administrative Costs. 1; Maintain quarterly reporting of all activities. 2; Provide for Board of Directors, audit, internet, postage & stationary costs for 3 ministries. 3; Support for INWAP participants. 4; Capacity Building for Workers in all sectors of ministry. 5; Maintain all school equipment. 6; Provide Administrative Vehicle (ministry visits). 7; Procure 4 administrative laptops. 8; Procure Colored Industrial Printer. 9; Pay outstanding and current gratuity packs for employees. - PROGRAMME BUDGET FOR FIVE YEARS Activity; Justification; Year 1 (2023) USD; Year 2 (2024) USD; Year 3 (2025) USD; Year 4 (2026) USD; Year 5 (2027) USD. Physical and Health development; Proposed; 465,140; 488,004; 560,204.40; 590,484.84; 696,813.32. 1; Establish a school clinic, hire workers and procure drugs at ZACTS OVC School.; Renovating the existing building as clinic; 8,600; 7,260; 7,986; 8,784.60; 9,663.06. 2; Provide sanitary pads for all girls from grade 5 to grade 12 in all ministries; Female pupils’ hygiene; 5,040; 5,544; 6,098.40; 6,708.24; 7,379.06. 3; Enhance feeding program for 2,500 children in 3 ministries; Children eat lunch daily INGAP; 432,000; 475,200; 522,720; 574,992; 632,491.20. 4; Organize bi-annual medical outreaches at ZACTS; Medical Team visits Through INCAP; 3,500; 4,200; 5,040. 5; Provide clean and potable water – 1 for school and 3 for the community.; Drilling boreholes; 16,000; 19,200; 42,240. Educational development; Proposed; 142,600; 83,710; 114,281; 163,689.10; 138,058.01. 1; Procure teaching and learning materials for ZACTS and Emele; Teachers & Learners books; 1,500; 1,650; 1,815; 1,996.50; 2,196.15. 2; Hold quarterly Continued Profession Development (CPD) sessions for teachers.; Teachers’ in-service training; 600; 660; 726; 798.60; 878.46. 3; Provide school uniforms for sponsored pupils; All grades; 15,500; 18,600; 22,320. 4; Enroll 100 pupils in two schools each year; November enrolments; 150; 165; 181.50; 199.65; 219.62. 5; Organize educational trips for students at ZACTS, Misaka and Emele; Education visit program; 350; 385; 423.50; 465.85; 512.44. 6; Pay salaries and wages to volunteer teachers at ZACTS and Emele; Motivation & upkeep; 25,200; 27,720; 30,492; 33,541.20; 36,895.32. 7; Uphold support for INCAP participants; On child assistance program; 4,500; 4,950; 5,445; 5,989.50; 6,588.45. 7; Support for 96 INSAP participants; College Students; 6,000; 6,600; 7,260; 7,986; 8,784.60. 8; Support INGAP participants in school; 650 Primary pupils 430 Secondary pupils; 37,800; 41,580; 45,738; 50,311.80; 55,342.98. 9.; Procure Home Economics Utensils; H E Classes equipment; 3,000; 3,600; 4,320. 10; Procure 40 computers; Compulsory ICT studies; 48,000; 62,400. Life Skills and Social development; Proposed; 18,400; 20,240; 22,264; 24,490.40; 26,939.44. 1; Form and support a tailoring club for young mothers who have dropped out of school.; 1-year Empowerment program (INGAP); 7,000; 7,700; 8,470; 9,317; 10,248.70. 2; Form and support a 10 women cooperative group that will be empowered through agricultural program each year.; Community empowerment program for women; 3,500; 3,850; 4,235; 4,658.50; 5,124.35. 3; Organize sporting activities for pupils at ZACTS and Emele.; School co-curricular activities; 400; 440; 484; 532.40; 585.64. 4; Procure sports equipment for sporting activities at ZACTS and Emele; Sports attire & equipment; 500; 550; 605; 665.50; 732.05. 5.; Enhance school Agricultural Activities; School production Unit; 7,000; 7,700; 8,470; 9,317; 10,248.70. Spiritual development and Value formation; Proposed; 2,500; 2,750; 3,025; 3,327.50; 3,660.25. 1; Form and provide Biblical materials to a Bible group of 200 pupils at ZACTS, Misaka and Emele.; Meet and provide snacks; 1,300; 1,430; 1,573; 1,730.30; 1,903.33. 2; Form Evangelism and Counselling Ministry; Outreach & transport; 1,200; 1,320; 1,452; 1,597.20; 1,756.92. Infrastructure development; Proposed; 134,200; 36,054; 155,239; 15,531.20; 58,843.92. 1; Construct 4 by 3 classroom blocks at ZACTS & Emele; Creation of classroom space; 29,000; 34,800; 41,760. 2; Construct 4 by 4 blocks of staff flats at ZACTS & Emele; Staff Accommodation; 62,000; 74,400. 3; Construct 2 ablution blocks for pupils in primary and secondary school at ZACTS and 1 block for Emele; Water-bone toilets; 14,000; 16,800. 4; Maintain school furniture, classroom blocks & houses; Maintenance works items; 1,200; 1,320; 1,452; 1,597.20; 1,756.92. 5; Construct 1 x 4 Farm office block; Fram manager, assistant & workers offices; 10,000. 6; Input storage shed; Agricultural farming inputs; 6,600. 7; Construct grain storage; Cereals and grain crops; 8,800. 8; Construct ware house; Tools and equipment; 6,000. 9; Construct Piggery house; Pigs rearing; 8,000. 10; Construct 4 farm dwelling houses; 4 farm workers; 19,334; 27,787; 13,934; 15,327. 11; Construct poultry security wall; Strict unnecessary entries & avoid diseases; 4,000. Agricultural Programs; proposed; 34,430; 38,792; 46,654; 51,282; 58,176. 1; Provide inputs for soya beans, groundnuts, sunflower and Maize; Seed & fertilizers; 4,237; 7,856; 12,624; 13,886; 15,275. 2; Procure fruit trees and its inputs (Oranges, lemons, guavas, Paw paws and Mangoes); Fruit trees for each type and top dressing; 2,433; 400; 440; 484; 532. 3; Provide inputs for broilers, layers, Rabbits, ducks, pigs and cattle rearing; Chicks, Livestock and feed; 12,160; 13376; 14,714; 17657; 21188. 4; Pay salaries and Gratuity packs for employees; Farm Manager, assistant and 6 workers; 15,600; 17,160; 18876; 19,255; 21,181. Administrative Costs; Proposed; 92,800; 69,300; 76,230; 83,853; 92,238.30. 1; Board of Directors, audit, internet, Zesco utilities, postage & stationery costs, for 3 ministries; Day to day operations of the ministries; 1500; 1,650; 1,815; 1,996.50; 2,196.15. 2; Quarterly reporting costs for all activities; Pupils’ letter writing and Project Reports; 700; 770; 847; 931.70; 1,024.87. 3.; Support for INWAP participants; Stipends for 4 INZ staff; 28,800; 31,680; 34,848; 38,332.80; 42,166.08. 4; Capacity Building for Workers in all sectors of ministry; In-service training for workers; 4,500; 4,950; 5,445; 5,989.50; 6,588.45. 5; Maintain all school equipment; School machinery services; 6,000; 6,600; 7,260; 7,986; 8,784.60. 6; Procure Administrative Vehicle; Ministry operations; 25,000. 7; Procure 4 administrative laptops; Easy administrative works and communication purpose; 4,800. 8; Pay outstanding & current staff gratuity; 35 members of Staff & workers; 21,500; 23,650; 26,015; 28,616.50; 31,478.15. 9; Procure Colored Industrial Printer; Printing purposes; 1,400. GRAND TOTALS PROPOSED; US $4,573,844.68 (ZMW68,307,670.20); 891,470; 773,850; 977,897.40; 932,658.04; 1,032,969.24. |